## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18223 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000295/2023-2024 | 2433/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 92.47 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18223 | Augmentation | Laying distribution system of piped water supply at Zone-IIA (JALABERIA) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-2 | ORD/000401/2021-2022 | 2597/SWD-I | 15/03/2022 | 13/07/2022 | SPA ENTERPRISE | 631.68 | 582.5 | 92.21 | 70
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18223 | Augmentation | Construction of 1250 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-II at Jalaberia Mouza of Kultali Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD | JE-2 | ORD/000014/2022-2023 | 866/SWD-I | 13/07/2022 | 09/05/2023 | M/S PATH MAKERS | 322.19 | 309.12 | 95.94 | 91
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18223 | Augmentation | Restoration of boundary wall at Headworks site of Zone-II within kultali block, under Augmentation of laying distribution system to extend the benefit of 100% Households in Zone-II at KULTALI block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur dist. South 24 Pgns. under South 24 Pgns. Water Supply Division-I, PHE Dte. (TSM/ 016053) | AE BSD | JE RWS | ORD/000250/2023-2024 | 1492/SWD-I | 19/07/2023 | 17/09/2023 | A.B. ASSOCIATES | 14.14 | 13.23 | 93.6 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18223 | Augmentation | joynagar Jalaberia Kultali Road from 7.47 Kmp to 8.00 Kmp restoration of Paver Block,from 8.00 Kmp to 9.5 Kmp & 16.0 Kmp to 18.50 Kmp restoration of Head Shoulder due to laying of pipes by PHED under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W(Roads) Directorate in the District of South 24 Parganas |  |  | BILL/00639/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 10.48 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE | SM/18223 | Augmentation | Laying distribution system of piped water supply at Zone-IIB (JALABARIA MOUZA) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-1 | ORD/000402/2021-2022 | 2600/SWD-I | 15/03/2022 | 24/11/2025 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 644.11 | 365.58 | 56.76 | 65
Total | [13 empty] | 1715.07 | 1270.44 | 74.07