## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Balance civil works of Kultali GLR under the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD | JE-2 | ORD/000006/2022-2023 | 839/SWD-I | 08/07/2022 | 19/12/2025 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD | 113.5 | 17.93 | 15.8 | 90
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Laying distribution system of piped water supply at Zone-VB of Kultali Block, under BARUIPUR Sub-Division, for ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-1 | ORD/000037/2022-2023 | 17/SWD-I | 06/04/2022 | 24/05/2025 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 589.08 | 68.62 | 11.65 | 50
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Laying distribution system of piped water supply at Zone-VA of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-1 | ORD/000874/2022-2023 | 16/SWD-I | 06/04/2022 | 09/03/2025 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 602.94 | 217.67 | 36.1 | 65
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 2956/SWD-I | 16/02/2023 | 16/02/2023 | Resource Division | 50.12 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 2979/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 37.62 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 2991/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 62.44 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 382/SWD-I | 27/04/2023 | 27/04/2023 | Resource Division | 119.44 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000297/2023-2024 | 2432/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 71.69 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Construction of protection wall for laying pipeline, restoration of damaged road due to laying of pipeline and other allied works for Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-V at KULTALI Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, PHE Dte. (SM/ 18224) (2nd call) |  |  | ORD/000740/2024-2025 | 4638/SWD-I | 14/11/2024 | 29/12/2024 | MOUMITA ENTERPRISE | 89.32 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Jamtala Petkulchand Road from 0.20 to 0.35 km, 4.50 to 6.00 km, 8.20 to 8.50 km, 8.80 to 9.00 km & 12.50 to 13.00 km Restoration of Brick top surface & Saucer drain in different chainage due to laying of pipelines by PHE Department under Lakshmikantapur Highway Sub Division of Diamond Harbour Highway Division in the District of South 24 Parganas. |  |  | BILL/00636/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 13.26 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-V at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE D | SM/18224 | Augmentation | Waterproofing of Reservoir at Kultali GLR under Augmentation of laying distribution system to extend the benefit of 100% household in Zone-V at KULTALI block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, Dist. South 24 Parganas under South 24 Parganas Water Supply Division-I, PHE Dte. (SM/18224) | AE BSD | JE-2 | ORD/000090/2025-2026 | 1765/SWD-I | 02/07/2025 | 01/08/2025 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 10.26 | 0 | 0 | 100
Total | [13 empty] | 1759.68 | 304.22 | 17.29