## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | SM/18253 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 248/SWD-I | 20/04/2023 | 20/04/2023 | Resource Division | 146.16 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | SM/18253 | Augmentation | Providing Balance FHTC for Budge Budge-II, Bishnupur-II and Mayapur GP with allied works in connection to Retrofitting and providing FHTC including Special Repair and Rejuvenation of different units of 34 MGD Treatment Plant at Dakshin Roypur for FHTC Drive under Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Pgns. District. [No. of FHTC = 23728] (TSM/014925) | AE S24D1 | JE-1 | ORD/000567/2023-2024 | 2649/SWD-I | 27/10/2023 | 25/01/2024 | WPIL LTD. | 1600.01 | 534.16 | 33.38 | 20
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | SM/18253 | Augmentation | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 16/12/2023 to 12/06/2024] [Vehicle No- WB-09-1333] | AE HQ-II | JE-2 | ORD/000762/2023-2024 | 3247/SWD-I | 15/12/2023 | 12/06/2024 | SUDIP GHOSH | 0.86 | 1.96 | 228.66 | 66
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | SM/18253 | Augmentation | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 13/06/2024 to 30/11/2024] [Vehicle No-WB-09-1333] | AE HQ-II,AE SWSD-I | JE-2 | ORD/000219/2024-2025 | 2572/SWD-I | 04/06/2024 | 22/11/2024 | SUDIP GHOSH | 0.81 | 2.15 | 264.42 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | SM/18253 | Augmentation | Retrofitting of old recirculation system of 34 MGD WTP (Civil Part) at Budge Budge II Block Under South 24 Pgns W/S Division-I, P.H.E Dte. | AE SWSD-I | JE-2 | ORD/000339/2023-2024 | 1608/SWD-I | 31/07/2023 | 14/10/2023 | S. ROY AND ASSOCIATES | 224.5 | 166.58 | 74.2 | 25
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | SM/18253 | Augmentation | Supply, delivery and installation of vertical turbine sewage pump with suitable rated vertical Induction motor set at WTP plant of Dakshin Roypur (34 MGD) with starter, cables, valves, pipe connections dismantling joints, and all other accessories & related allied works under SMD, PHE Dte. | Assistant Engineer -II | Junior Engineer | ORD/000722/2024-2025 | 3673/SMD | 21/11/2024 | 15/05/2026 | S.P. CONSTRUCTION | 106.17 | 0 | 0 | 60
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | SM/18253 | Augmentation | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 01/12/2024 to 31/05/2025] [Vehicle No-WB-09-1333] | AE SWSD-I | JE-2 | ORD/000890/2024-2025 | 4877/SWD-I | 29/11/2024 | 30/05/2025 | SUDIP GHOSH | 0.86 | 2.18 | 251.72 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | SM/18253 | Augmentation | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 01/06/2025 to 30/11/2025] [Vehicle No-WB-09-1333] | AE SWSD-I | JE-2 | ORD/000060/2025-2026 | 1369/SWD-I | 22/05/2025 | 21/11/2025 | SUDIP GHOSH | 0.87 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Retrofitting and proving FHTC including special repair and rejuvenation of different units of 34 MGD treatment plant at DAKSHIN ROYPUR for FHTC drive under surface water based W/S scheme in the Arsenic affected areas of South 24-pgns District. | SM/18253 | Augmentation | Retrofitting including Special Repair and Rejuvenation of different units of 34 MGD Treatment Plant at Dakshin Roypur for FHTC Drive under Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/014925] | AE SWSD-I | JE-2 | ORD/000569/2023-2024 | 2666/SWD-I | 31/10/2023 | 23/01/2025 | VISHVARAJ ENVIRONMENT PRIVATE LIMITED | 515.38 | 323.59 | 62.79 | 80
Total | [13 empty] | 2595.63 | 1030.61 | 39.71