## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based ABJAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/18266 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Abjakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/001434/2022-2023 | 148/SMD | 16/01/2023 | 16/04/2023 | S.P. CONSTRUCTION | 33.56 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ABJAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/18266 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Abjakhali Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000961/2022-2023 | 1139/SWD-I | 25/08/2022 | 24/09/2022 | GEO SOLUTION | 2.85 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ABJAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/18266 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 323/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 84.26 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ABJAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/18266 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ABJAKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017506] | AE SWSD-II | JE4 | ORD/000226/2023-2024 | 1402/SWD-I | 14/07/2023 | 13/08/2023 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 15.86 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ABJAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/18266 | Augmentation | Laying of rising main and additional pipelines for distribution system, construction of boundary wall, approach road, land development, pipeline protection and road restoration for ABJAKHALI PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/18266] | AE SWSD-II | JE4 | ORD/000254/2024-2025 | 2671/SWD-I | 07/06/2024 | 22/07/2024 | AVIK ENTERPRISE | 96.46 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ABJAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/18266 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of ABJAKHALI PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 3239) [TSM/017506]. | AE SWSD-II | JE4 | ORD/000306/2023-2024 | 1695/SWD-I | 07/08/2023 | 01/04/2025 | PRASUN ENTERPRISE | 495.25 | 0 | 0 | 70
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based ABJAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas o | SM/18266 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Abjakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/001569/2024-2025 | 2030/SMD | 28/06/2024 | 26/09/2024 | S.P. CONSTRUCTION | 33.56 | 0 | 0 | 0
Total | [13 empty] | 761.8 | 0 | 0