## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18268 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000289/2023-2024 | 2414/SWD-I | 30/09/2023 |  | Resource Division | 50.05 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18268 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000309/2023-2024 | 2736/SWD-I | 06/11/2023 |  | Resource Division | 18.66 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18268 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Mirzapur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000979/2022-2023 | 1435/SWD-I | 23/09/2022 | 23/10/2022 | GEO SOLUTION | 2.76 | 1.36 | 49.39 | 100
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18268 | Augmentation | Quotation for new service connection at P.H. NO.2 of Mirzapur w/s scheme . Application number:1007729941. |  |  | BILL/00535/2024-2025 | BP-2024-25-129 | 24/06/2024 |  | WBSEDCL | 4.82 | 0 | 0 | null
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18268 | Augmentation | Quotation for new service connection at P.H. NO.2 of Mirzapur w/s scheme . Application number:1007729941. |  |  | BILL/00535/2024-2025 | BP-2024-25-129 | 24/06/2024 |  | WBSEDCL | 4.82 | 0 | 0 | null
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18268 | Augmentation | Extension of Boundary wall and development of land at 2nd and 3rd Tubewell site for MIRZAPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/18268) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000291/2024-2025 | 3108/SWD-I | 09/07/2024 | 23/08/2024 | BISWAS CONSTRUCTION | 23.23 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18268 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Mirzapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/001965/2023-2024 | 2280/SMD | 22/06/2023 | 20/09/2023 | M/S. S.S. ENTERPRISE | 33.56 | 2.43 | 7.23 | 31
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18268 | Augmentation | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 09 (nine) nos. chlorination room of size 5.0m x 4.0m for JALDHAPA, SHYAMPUR (PART-II) & MIRZAPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9688] [TSM/017282, TSM/017546, TSM/016565] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000280/2023-2024 | 1552/SWD-I | 25/07/2023 | 20/05/2024 | S & P ENTERPRISE | 1745.38 | 87.65 | 5.02 | 6
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MIRZAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18268 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MIRZAPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [TSM/016565] [2nd Call] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000228/2023-2024 | 1404/SWD-I | 14/07/2023 | 13/08/2023 | M/S SACHIDULAL CHOWDHURY | 47.53 | 7.57 | 15.93 | 80
Total | [13 empty] | 1930.78 | 99.01 | 5.13