## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chandpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/001420/2022-2023 | 3459/SMD | 23/12/2022 | 23/03/2023 | TRIO CONCERN | 26.99 | 12.93 | 47.91 | 50
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Construction of 450 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 3295] | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000291/2023-2024 | 1622/SWD-I | 02/08/2023 | 01/04/2025 | SAFECO ENTERPRISES | 683.19 | 230.67 | 33.76 | 20
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHANDPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/016315] | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000297/2023-2024 | 1662/SWD-I | 03/08/2023 | 23/02/2025 | PADMA ENGINEERING CO. | 3.14 | 1.57 | 50 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR CHANDPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/016315) | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000298/2023-2024 | 1663/SWD-I | 03/08/2023 | 22/02/2025 | PADMA ENGINEERING CO. | 30.07 | 11.8 | 39.23 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1721/SWD-I | 08/08/2023 | 08/08/2023 | Resource Division | 22.24 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04230/2023-2024 | BP-2023-24-436 | 27/12/2023 | 27/12/2023 | WBSEDCL | 3.92 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Additional Laying Pipeline for 63mm dia (OD) & 75mm dia (OD) HDPE pipe under ¿CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM.¿ [SM/18328] | Assistant engineer (contractual) | JE-3 | ORD/000544/2024-2025 | 4101/SWD-I | 20/09/2024 | 30/09/2024 | SAFECO ENTERPRISES | 27.53 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Chandpur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002247/2023-2024 | 132/SMSD | 02/02/2024 | 17/02/2024 | TRIO CONCERN | 0.58 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/18328) | Assistant engineer (contractual) | JE-3 | ORD/000240/2024-2025 | 2660/SWD-I | 07/06/2024 | 15/10/2025 | M/S ASHA ENGINEERING | 10.58 | 0 | 0 | 60
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Construction of Boundary Wall, Pathway, Drain and other allied works of CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18328) |  |  | ORD/000887/2024-2025 | 4992/SWD-I | 05/12/2024 | 03/02/2025 | SAFECO ENTERPRISES | 38.98 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Chandpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002201/2023-2024 | 133/SMSD | 02/02/2024 | 17/02/2024 | TRIO CONCERN | 0.92 | 0.92 | 99.62 | 100
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000316/2023-2024 | 246/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 20.3 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.17] |  |  | BILL/00476/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 14.02 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18328 | Augmentation | Charges for new service connection at pump house no-II of Chandpur (Sonarpur Block) |  |  | BILL/02619/2024-2025 | BP-2024-25-562 | 28/01/2025 | 28/01/2025 | WBSEDCL | 4.63 | 0 | 0 | 0
Total | [13 empty] | 887.08 | 257.88 | 29.07