## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RASHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18331 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Rashkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/001432/2022-2023 | 147/SMD | 16/01/2023 | 16/04/2023 | S.P. CONSTRUCTION | 33.46 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RASHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18331 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Raskhali Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000947/2022-2023 | 1128/SWD-I | 24/08/2022 | 23/09/2022 | GEO SOLUTION | 2.94 | 2.94 | 100 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RASHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18331 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 323/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 88.83 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RASHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18331 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for Proposed RASHKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 3624] | AE SWSD-II | JE2 | ORD/000419/2023-2024 | 1965/SWD-I | 24/08/2023 | 02/10/2025 | M/S N. H. ENTERPRISE | 448.48 | 98.33 | 21.92 | 20
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based RASHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18331 | Augmentation | Laying of rising main and additional pipeline for distribution system, construction of Boundary Wall, pump house, approach road and land development for RASHKHALI Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/18331) | AE SWSD-II | JE2 | ORD/000774/2024-2025 | 4760/SWD-I | 21/11/2024 | 21/02/2026 | M/S N.H. ENTERPRISE | 208.36 | 0 | 0 | 15
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based RASHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18331 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Rashkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/001568/2024-2025 | 2029/SMD | 28/06/2024 | 26/09/2024 | S.P. CONSTRUCTION | 33.46 | 0 | 0 | 0
Total | [13 empty] | 815.53 | 101.27 | 12.42