## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18497 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1721/SWD-I | 08/08/2023 | 08/08/2023 | Resource Division | 18.81 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18497 | Augmentation | Construction of Boundary Wall,Land Development, Pathway,Drain & others allied works of Jagadishpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/18497] | Assistant engineer (contractual) | JE-3 | ORD/000842/2023-2024 | 1208/SWD-I | 11/03/2024 | 25/04/2024 | G.B. CONSTRUCTION AND CO. (DUMDUM) | 46.14 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18497 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "JAGADISHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/18497) | Assistant engineer (contractual) | JE-3 | ORD/000244/2024-2025 | 2664/SWD-I | 07/06/2024 | 22/07/2024 | JYOTI ENTERPRISE | 10.26 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18497 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for JAGADISHPUR PWSS of Sonarpur Blockfor Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/017715] | AE HQ-I | JE-3 | ORD/000293/2023-2024 | 1658/SWD-I | 03/08/2023 | 02/09/2023 | TAPAS KUMAR GIRI | 31.8 | 30.85 | 97.01 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18497 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000319/2023-2024 | 255/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 15.42 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18497 | Augmentation | Charges for service connection at Pump house no-II of Jagadishpur (Sonarpur Block) |  |  | BILL/00395/2024-2025 | BP-2024-25-93 | 10/06/2024 | 10/06/2024 | WBSEDCL | 7.05 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18497 | Augmentation | Charges for new service connection at Jagadishpur pump house-I (Sonarpur Block) |  |  | BILL/00394/2024-2025 | BP-2024-25-92 | 10/06/2024 | 10/06/2024 | WBSEDCL | 10.06 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18497 | Augmentation | Construction of 350 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for JAGADISHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2503) (TSM/017715) | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000426/2023-2024 | 1986/SWD-I | 25/08/2023 | 01/11/2025 | G.B. CONSTRUCTION AND CO. | 703.02 | 274.19 | 39 | 50
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for JAGADISHPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18497 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Jagadishpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000120/2023-2024 | 1097/SMD | 18/04/2023 | 01/05/2025 | DEBJYOTI BASU | 22.79 | 0 | 0 | 100
Total | [13 empty] | 865.35 | 305.04 | 35.25