## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | SM/18499 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Debipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/001520/2022-2023 | 916/SMD | 30/03/2023 | 28/06/2023 | M/S. S.S. ENTERPRISE (DOMKAL) | 25.09 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | SM/18499 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1727/SWD-I | 09/08/2023 | 09/08/2023 | Resource Division | 22.96 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | SM/18499 | Augmentation | Construction of 400 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for DEBIPUR Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2830) (TSM/018469) | AE HQ-I,AE HQ-II | JE-4 | ORD/000534/2023-2024 | 2360/SWD-I | 26/09/2023 | 22/07/2024 | THE TEESTA CONSTRUCTION | 780.87 | 46.99 | 6.02 | 25
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | SM/18499 | Augmentation | Development of land, construction of approach road and other allied works at HW site & 2nd Tubewell site of "DEBIPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Pgns. W/S Division-I, PHE Dte. for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under Jal Jeevan Mission". (SM/18499) |  |  | ORD/000538/2024-2025 | 4095/SWD-I | 20/09/2024 | 19/11/2024 | M/S SONALI CONSTRUCTION | 39.61 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | SM/18499 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of DEBIPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/18499] |  |  | ORD/000755/2024-2025 | 4676/SWD-I | 18/11/2024 | 17/01/2025 | SUJIT KUMAR SHARMA | 31.4 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | SM/18499 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000323/2023-2024 | 253/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 17.43 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | SM/18499 | Augmentation | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DEBIPUR PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018469] | AE HQ-I | JE-4 | ORD/000303/2023-2024 | 1671/SWD-I | 04/08/2023 | 06/03/2025 | M/S BANERJEE ENGINEERING SYSTEM | 31.79 | 3.6 | 11.34 | 50
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | SM/18499 | Augmentation | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under NALMURI, DEBIPUR & NARAYANPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18548, SM/18499 & SM/18547) | AE HQ-I | JE-4 | ORD/000507/2024-2025 | 3976/SWD-I | 11/09/2024 | 10/03/2025 | TELETONE INDIA PRIVATE LIMITED | 70.04 | 16.06 | 22.93 | 60
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for DEBIPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Unde | SM/18499 | Augmentation | Additional Laying of distribution Network System for different dia HDPE pipe & Road Restoration for DEBIPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18499) |  |  | ORD/000020/2025-2026 | 972/SWD-I | 09/04/2025 | 24/05/2025 | THE TEESTA CONSTRUCTION | 71.48 | 0 | 0 | 0
Total | [13 empty] | 1090.68 | 66.66 | 6.11