## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18500 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1727/SWD-I | 09/08/2023 | 09/08/2023 | Resource Division | 17.47 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18500 | Augmentation | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SERPUR PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018414] | AE HQ-I | JE-4 | ORD/000362/2023-2024 | 1771/SWD-I | 11/08/2023 | 10/09/2023 | JSSM CONSTRUCTION | 31.72 | 0 | 0 | 50
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18500 | Augmentation | Construction of 450 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for SERPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 2549) (TSM/018414) | AE HQ-I,AE HQ-II | JE RWS, Bhangar-II Block,JE-4 | ORD/000421/2023-2024 | 1968/SWD-I | 24/08/2023 | 19/06/2024 | SAMSUL ENTERPRISE | 468.39 | 108.36 | 23.14 | 20
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18500 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000327/2023-2024 | 249/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 15.7 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18500 | Augmentation | Quotation for new service ( power) connection at Serpur PH-1, Water supply scheme under Bhangar-I block Reference ID106663976 Application No-1007921408 |  |  | BILL/01682/2024-2025 | BP-2024-25-395 | 27/09/2024 | 27/09/2024 | WBSEDCL | 22.96 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18500 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Serpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/001526/2022-2023 | 932/SMD | 30/03/2023 | 31/03/2025 | S. DUTTA | 25.42 | 0 | 0 | 35
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | SERPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18500 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of SERPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18500) |  |  | ORD/001084/2024-2025 | 5212/SWD-I | 20/12/2024 | 18/02/2025 | SAMSUL ENTERPRISE | 64.9 | 0 | 0 | 0
Total | [13 empty] | 646.57 | 108.36 | 16.76