## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18501 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Tardaha Kapasati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/001518/2022-2023 | 907/SMD | 28/03/2023 | 26/06/2023 | S. DUTTA | 25.09 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18501 | Augmentation | Construction of 450 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for TARDAHA KAPASATI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 3298) (TSM/018470) | AE HQ-I | JE-4 | ORD/000354/2023-2024 | 1740/SWD-I | 10/08/2023 | 05/06/2024 | MRA NIRMAN UDYOG | 1034.36 | 663.37 | 64.13 | 35
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18501 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for TARDAHA KAPASATI PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018470] | AE HQ-II | JE-4 | ORD/000301/2023-2024 | 1666/SWD-I | 03/08/2023 | 02/09/2023 | ASIT PRAMANIK | 31.76 | 30.2 | 95.1 | 99
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18501 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1727/SWD-I | 09/08/2023 | 09/08/2023 | Resource Division | 44.58 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18501 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of TARDAH KAPASATI PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18501) |  |  | ORD/000678/2024-2025 | 4467/SWD-I | 29/10/2024 | 12/01/2025 | MRA NIRMAN UDYOG | 201.31 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18501 | Augmentation | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under TARDAH KAPASATI, BHATIPOTA, KHARAMBA & SHERPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18501, SM/13341, SM/18545 & SM/18500) | AE HQ-I | JE-4 | ORD/000508/2024-2025 | 3977/SWD-I | 11/09/2024 | 26/10/2024 | TELETONE INDIA PRIVATE LIMITED | 107.09 | 8.03 | 7.5 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18501 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000321/2023-2024 | 256/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 20.32 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | TARDAHA KAPASATI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18501 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. no.37] |  |  | BILL/00467/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 65.69 | 0 | 0 | 0
Total | [13 empty] | 1530.19 | 701.61 | 45.85