## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Jagatipota water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000121/2023-2024 | 1103/SMD | 19/04/2023 | 18/07/2023 | JAGANNATH ENTERPRISE | 21.77 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1721/SWD-I | 08/08/2023 | 08/08/2023 | Resource Division | 17.9 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01989/2023-2024 | BP-2023-24-239 | 11/09/2023 | 11/09/2023 | WBSEDCL | 4.84 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for JAGATIPOTA PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018121] | AE HQ-I | JE-3 | ORD/000294/2023-2024 | 1659/SWD-I | 03/08/2023 | 02/09/2023 | TAPAS KUMAR GIRI | 31.8 | 15.5 | 48.75 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Construction of 300 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for JAGOTIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1766) (TSM/018121) | AE HQ-I | JE-3 | ORD/000420/2023-2024 | 1967/SWD-I | 24/08/2023 | 19/06/2024 | SAMSUL ENTERPRISE | 617.72 | 312.03 | 50.51 | 20
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Jagatipota scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/000296/2024-2025 | 1013/SMSD | 11/07/2024 | 26/07/2024 | JAGANNATH ENTERPRISE | 0.89 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Jadatipota W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/000297/2024-2025 | 938/SMSD | 28/06/2024 | 13/07/2024 | JAGANNATH ENTERPRISE | 0.58 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Construction of Boundary Wall, Pathway, Drain, Development of land & others allied works of JAGATIPOTA PWSS within Sonarpur Block "JAGATIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18546) | Assistant engineer (contractual) | JE-3 | ORD/000825/2023-2024 | 1299/SWD-I | 15/03/2024 | 29/04/2024 | SAMSUL ENTERPRISE | 43.64 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Jagatipota W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002202/2023-2024 | 264/SMSD | 23/02/2024 | 09/03/2024 | JAGANNATH ENTERPRISE | 0.89 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Construction of Hume Pipe Culvert 4.80 Mtr.span with 23 Mtr.Long temporary approach road at OHR Site of "JAGATIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18546) | Assistant engineer (contractual) | JE-3 | ORD/000529/2024-2025 | 4075/SWD-I | 19/09/2024 | 19/10/2024 | SAMSUL ENTERPRISE | 13.07 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for JAGATIPOTA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Un | SM/18546 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000320/2023-2024 | 257/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 10.88 | 0 | 0 | 0
Total | [13 empty] | 763.98 | 327.53 | 42.87