## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1719/SWD-I | 08/08/2023 | 08/08/2023 | Resource Division | 23.63 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Construction of pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for NARAYANPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 2308) (TSM/018316) | AE HQ-I,AE HQ-II | JE RWS, Bhangar-II Block,JE-4 | ORD/000396/2023-2024 | 1877/SWD-I | 18/08/2023 | 16/11/2023 | ATCO ENTERPRISE | 380.84 | 198.35 | 52.08 | 45
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of NARAYANPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18547) |  |  | ORD/000704/2024-2025 | 4506/SWD-I | 30/10/2024 | 29/12/2024 | ATCO ENTERPRISE | 92.01 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Protection of pipeline of distribution of N.P-300-348, 39-35, 21-14, 13-08, 20-25, 27-37, 37-49, 52-66, 66-32 & 143-182 of Narayanpur Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18547) |  |  | ORD/000828/2023-2024 | 1109/SWD-I | 05/03/2024 | 20/03/2024 | ATCO ENTERPRISE | 9.78 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000328/2023-2024 | 258/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 14.22 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Quotation for new service(power) connection at Narayanpur PH -2 water supply scheme under bhangar-I block Reference ID-106550931, Application No- 1007657658 |  |  | BILL/00983/2024-2025 | BP-2024-25-212 | 30/07/2024 | 30/07/2024 | WBSEDCL | 17.32 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.40] |  |  | BILL/00470/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 39.52 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmnetation of Narayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/001522/2022-2023 | 929/SMD | 30/03/2023 | 31/03/2025 | RELIABLE CONSTRUCTION | 25.41 | 0 | 0 | 35
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under NALMURI, DEBIPUR & NARAYANPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18548, SM/18499 & SM/18547) | AE HQ-I | JE-4 | ORD/000507/2024-2025 | 3976/SWD-I | 11/09/2024 | 10/03/2025 | TELETONE INDIA PRIVATE LIMITED | 70.04 | 14.58 | 20.81 | 60
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for NARAYANPUR PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018316] | AE HQ-I | JE-4 | ORD/000302/2023-2024 | 1673/SWD-I | 04/08/2023 | 03/09/2023 | MOUSUMI DAS SARKAR | 31.72 | 14.65 | 46.18 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 of Narayanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) | Assistant Engineer | Junior Engineer | ORD/002161/2024-2025 | 374/SMSD | 12/03/2025 | 27/03/2025 | RELIABLE CONSTRUCTION | 0.29 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Narayanpur PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002162/2024-2025 | 369/SMSD | 12/03/2025 | 27/03/2025 | RELIABLE CONSTRUCTION | 0.92 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for NARAYANPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18547 | Augmentation | Additional Quotation for Narayanpur PH-2 Water supply scheme under Bhangar-I Block Reference ID-860336253, Application Nos-100000138243 |  |  | BILL/00672/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 0.24 | 0 | 0 | 0
Total | [13 empty] | 705.95 | 227.57 | 32.24