## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18548 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Nalmuri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/001517/2022-2023 | 905/SMD | 28/03/2023 | 26/06/2023 | M/S. GHOSH ENTERPRISE | 25.41 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18548 | Augmentation | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for NALMURI PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018471] | AE HQ-I | JE-4 | ORD/000304/2023-2024 | 1672/SWD-I | 04/08/2023 | 03/09/2023 | M/S BANERJEE ENGINEERING SYSTEM | 31.79 | 14.74 | 46.36 | 50
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18548 | Augmentation | Construction of 350 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for NALMURI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 2582) (TSM/018471) | AE HQ-I,AE HQ-II | JE-4 | ORD/000439/2023-2024 | 2089/SWD-I | 29/08/2023 | 19/09/2025 | SE TILES MANUFACTURING COMPANY PRIVATE LIMITED | 708.85 | 105.17 | 14.84 | 30
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18548 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1719/SWD-I | 08/08/2023 | 08/08/2023 | Resource Division | 28.02 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18548 | Augmentation | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under NALMURI, DEBIPUR & NARAYANPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18548, SM/18499 & SM/18547) | AE HQ-I | JE-4 | ORD/000507/2024-2025 | 3976/SWD-I | 11/09/2024 | 10/03/2025 | TELETONE INDIA PRIVATE LIMITED | 70.04 | 0 | 0 | 60
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18548 | Augmentation | Construction of approach Road for NALMURI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18548) | AE HQ-I | JE-4 | ORD/000830/2023-2024 | 1111/SWD-I | 05/03/2024 | 01/03/2025 | SUJIT KUMAR SHARMA | 10.92 | 2.87 | 26.32 | 90
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18548 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000326/2023-2024 | 250/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 15.91 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | NALMURI piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18548 | Augmentation | Land Developement Protection work for pipeline, construction of Boundary Wall with Internal Pavement and others allied works at HW & 2nd Tube-well site of NALMURI PWSS to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18548) |  |  | ORD/000107/2025-2026 | 1869/SWD-I | 14/07/2025 | 27/09/2025 | SUJIT KUMAR SHARMA | 161.85 | 0 | 0 | 0
Total | [13 empty] | 1052.8 | 122.79 | 11.66