## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BHANGAR RAGHUNATHPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/18569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1719/SWD-I | 08/08/2023 | 08/08/2023 | Resource Division | 20.72 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BHANGAR RAGHUNATHPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/18569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000322/2023-2024 | 254/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 17.46 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for BHANGAR RAGHUNATHPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/18569 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Raghunathpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000589/2023-2024 | 2625/SMD | 08/08/2023 | 01/04/2025 | MAHAMAYA ENTERPRISE | 38.9 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BHANGAR RAGHUNATHPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/18569 | Augmentation | Construction of 350 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for BHANGAR RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2835) (TSM/018465) | AE HQ-I,AE HQ-II | JE-4 | ORD/000394/2023-2024 | 1879/SWD-I | 18/08/2023 | 23/02/2026 | SHIV CONSTRUCTION | 477.4 | 0 | 0 | 20
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BHANGAR RAGHUNATHPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/18569 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of BHANGAR RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18569) | AE HQ-I | JE-4 | ORD/000563/2024-2025 | 4236/SWD-I | 30/09/2024 | 24/11/2025 | SUJIT KUMAR SHARMA | 68.52 | 0 | 0 | 60
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for BHANGAR RAGHUNATHPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/18569 | Augmentation | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for Bhangar Raghunathpur Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under Jal Jeevan Mission. [SM/18569] | AE HQ-I | JE-4 | ORD/000076/2025-2026 | 1579/SWD-I | 11/06/2025 | 02/12/2025 | PADMA ENGINEERING CO. | 15.9 | 0 | 0 | 100
Total | [13 empty] | 638.9 | 0 | 0