## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1721/SWD-I | 08/08/2023 |  | Resource Division | 23.28 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Bidyadharpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000990/2022-2023 | 1502/SWD-I | 28/09/2022 | 28/10/2022 | GEO SOLUTION | 2.9 | 1.45 | 49.77 | 100
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00005/2024-2025 | BP-2024-25-15 | 12/04/2024 |  | WBSEDCL | 4.76 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Construction of 500 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for BIDYADHARPUR Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2838) (TSM/019595) | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000447/2023-2024 | 2102/SWD-I | 30/08/2023 | 25/06/2024 | O.K. CONSTRUCTION | 627.54 | 169.96 | 27.08 | 20
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "BIDYADHARPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/18571)" |  |  | ORD/000232/2024-2025 | 2652/SWD-I | 07/06/2024 | 22/07/2024 | SUJOY SADHUKHAN | 10.55 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BIDYADHARPUR PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/019595] | AE HQ-I | JE-3 | ORD/000371/2023-2024 | 1780/SWD-I | 11/08/2023 | 26/08/2023 | MOULI CONSTRUCTION | 31.76 | 7.66 | 24.13 | 50
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bidyadharpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002842/2023-2024 | 292/SMSD | 07/03/2024 | 22/03/2024 | PS & ASSOCIATES | 0.92 | 0.46 | 49.81 | 100
8 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bidyadharpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/000302/2024-2025 | 923/SMSD | 28/06/2024 | 13/07/2024 | PS & ASSOCIATES | 0.92 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Bidyadharpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000592/2023-2024 | 2616/SMD | 07/08/2023 | 05/11/2023 | M/S. PS & ASSOCIATES | 25.92 | 5.93 | 22.88 | 40
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.18] |  |  | BILL/00477/2024-2025 | BP-2024-25-293 | 11/09/2024 |  | WBSRDA SOUTH 24 PGS ALIPORE | 10.46 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based BIDYADHARPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 parganas w/s Division-I, South 24 Parganas district for AUGMENTATION of Surface water based water supply scheme in the Arsenic Affected areas of | SM/18571 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.18] |  |  | BILL/00477/2024-2025 | BP-2024-25-293 | 11/09/2024 |  | WBSRDA SOUTH 24 PGS ALIPORE | 10.46 | 0 | 0 | 0
Total | [13 empty] | 749.46 | 185.46 | 24.75