## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Construction of 450 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2856) (TSM/018472) | AE HQ-I,AE HQ-II | JE-4 | ORD/000375/2023-2024 | 1799/SWD-I | 14/08/2023 | 02/07/2026 | MAJUMDER ENTERPRISE | 476.89 | 278.95 | 58.49 | 30
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gobindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000590/2023-2024 | 2648/SMD | 11/08/2023 | 02/04/2025 | SRI KRISHNA NIRMAN | 25.68 | 0 | 0 | 70
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GOBINDAPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018472] (2nd Call) | AE HQ-I,AE HQ-II | JE-4 | ORD/000366/2023-2024 | 1775/SWD-I | 11/08/2023 | 10/09/2023 | M/S SUNDARI CONSTRUCTION | 31.61 | 25.87 | 81.85 | 50
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1719/SWD-I | 08/08/2023 | 08/08/2023 | Resource Division | 22.96 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of GOBINDAPUR PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18572) | AE HQ-I | JE-4 | ORD/000930/2024-2025 | 5062/SWD-I | 10/12/2024 | 08/07/2026 | MAJUMDER ENTERPRISE | 172.05 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Gobindapur PH-2 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/18572) | Assistant Engineer | Junior Engineer | ORD/001621/2024-2025 | 1541/SMSD | 21/11/2024 | 06/12/2024 | SRI KRISHNA NIRMAN | 0.9 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000324/2023-2024 | 252/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 17.59 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.44] |  |  | BILL/00473/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 47.79 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Quotation for new service (power) connection at Gobindapur PH-1 , Water supply scheme under Bhangar-I Block. Reference ID-106663977, Application No- 1007921431 |  |  | BILL/01464/2024-2025 | BP-2024-25-345 | 09/09/2024 | 09/09/2024 | WBSEDCL | 5.42 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Bhangor Kulti Canal from 0.00 kmp to 2.00kmp, Permanent restoration work, damaged due tp " Pipeline Laying of 90mm to 280mm dia HDPE Pipe Line along flank by PHE DEpartment " within Alipore Highway sub-Division under South 24 Parganas Highway Division in the district of South 24 Parganas. (SM/18572) |  |  | BILL/00642/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 14.93 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Quotation for new service (power) connection at Gobindapur PH-2 , Water supply scheme under Bhangar-I Block. Reference ID-106663974, Application No- 1007921442 |  |  | BILL/01469/2024-2025 | BP-2024-25-346 | 09/09/2024 | 09/09/2024 | WBSEDCL | 5.37 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Gobindapur W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) | Assistant Engineer | Junior Engineer | ORD/002270/2024-2025 | 62/SMSD | 17/01/2025 | 01/02/2025 | SRI KRISHNA NIRMAN | 0.59 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Gobindapur PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/18572) | Assistant Engineer | Junior Engineer | ORD/001619/2024-2025 | 21/SMSD | 06/01/2025 | 21/01/2025 | SRI KRISHNA NIRMAN | 0.9 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Detailed project report for GOBINDAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District U | SM/18572 | Augmentation | Additional Quotation(WBSEDCL) for Gobindapur PH-I Water supply scheme under Bhangar-I Block. Reference ID- 860339053 Application ID- 100000140983 |  |  | BILL/01296/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 2.43 | 0 | 0 | 0
Total | [13 empty] | 825.11 | 304.82 | 36.94