## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 ,3 & 4 for Augmentation of Akna Mirzapur ( Zone-29) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000751/2023-2024 | 2693/SMD | 17/08/2023 | 15/11/2023 | NUPUR CHANDRA HALDER | 44.46 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based AKNA MIRJAPUR Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000919/2022-2023 | 1170/SWD-I | 30/08/2022 | 29/09/2022 | ASTER CONSULTANCY | 3.34 | 3.3 | 98.84 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 31.31 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Restoration of road after laying of pipeline, protection work for pipeline, development of land and other allied works for Ground water based AKNA MIRZAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/18573) |  |  | ORD/000332/2024-2025 | 3270/SWD-I | 22/07/2024 | 05/09/2024 | MONDAL AND CO | 50.41 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Akna Mirzapur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/18573) | Assistant Engineer | Junior Engineer | ORD/000220/2024-2025 | 941/SMSD | 28/06/2024 | 13/07/2024 | NUPUR CHANDRA HALDER | 0.58 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Akna Mirzapur water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/18573) | Assistant Engineer | Junior Engineer | ORD/000217/2024-2025 | 936/SMSD | 28/06/2024 | 13/07/2024 | NUPUR CHANDRA HALDER | 0.89 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Akna Mirzapur water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/18573) | Assistant Engineer | Junior Engineer | ORD/000218/2024-2025 | 937/SMSD | 28/06/2024 | 13/07/2024 | NUPUR CHANDRA HALDER | 0.89 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04651/2023-2024 | BP-2023-24-488 | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.19 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Road restoration of 070- Atghora on L068 To Tagarberia(WB/02/320) |  |  | BILL/01779/2024-2025 | BP-2024-25-804 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.75 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of AKNA MIRZAPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4257] [TSM/018363] | AE BSD | JE-1 | ORD/000407/2023-2024 | 1924/SWD-I | 22/08/2023 | 27/03/2025 | MONDAL AND CO | 592.29 | 336.64 | 56.84 | 70
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based AKNA MIRZAPUR (ZONE-29) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas di | SM/18573 | Augmentation | Construction of Platform for providing FHTC for Ground Water Based AKNA MIRZAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/18573) | AE BSD | JE-1 | ORD/000305/2024-2025 | 3218/SWD-I | 18/07/2024 | 16/09/2024 | MONDAL AND CO | 79.25 | 0 | 0 | 46
Total | [13 empty] | 810.35 | 339.95 | 41.95