## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Kannyanagar Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000962/2022-2023 | 1166/SWD-I | 29/08/2022 | 28/09/2022 | GEO SOLUTION | 2.92 | 2.92 | 100 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of KANNYANAGAR PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 4562) [TSM/018432]. | AE SWSD-II | JE4 | ORD/000427/2023-2024 | 1987/SWD-I | 25/08/2023 | 01/07/2025 | DEBAPRASAD MONDAL | 527.21 | 0 | 0 | 45
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Kanyanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000594/2023-2024 | 2692/SMD | 17/08/2023 | 15/11/2023 | NITESH MANAGEMENT | 34.41 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of KANNYANAGAR PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018432] | AE SWSD-II |  | ORD/000415/2023-2024 | 1959/SWD-I | 24/08/2023 | 23/10/2023 | T. K. ENTERPRISE | 18.3 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Construction of 03 (three) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for KANNYANAGAR, BAGI & BHANDARIA PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/018432, TSM/017332, TSM/017323] | AE SWSD-II | JE1,JE4 | ORD/000422/2023-2024 | 1969/SWD-I | 24/08/2023 | 19/06/2024 | H. T. R. CONSTRUCTION | 572.68 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KANNYANAGAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018432] | AE SWSD-II | JE4 | ORD/000376/2023-2024 | 1802/SWD-I | 14/08/2023 | 17/01/2025 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 15.85 | 0 | 0 | 98
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 323/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 49.9 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Construction of boundary wall, approach road, laying of rising main and other allied works for KANYANAGAR PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/12234] | AE SWSD-II | JE4 | ORD/000250/2024-2025 | 2670/SWD-I | 07/06/2024 | 22/07/2024 | CHANDAN ROY | 96.96 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Sinking of 02 (Two) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd and 3rd tubewell site for KANYANAGAR Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/18574) | AE SWSD-II | JE4 | ORD/000686/2024-2025 | 4481/SWD-I | 30/10/2024 | 31/01/2025 | MONDAL TUBEWELL | 31.72 | 0 | 0 | 98
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Land development at 3rd Tubewell site and approach road of Kannyanagar PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgs. W/S Divn.-I, P.H.E. Dte., for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (SM/18574) | AE SWSD-II | JE4 | ORD/000005/2025-2026 | 908/SWD-I | 02/04/2025 | 02/05/2025 | CHANDAN ROY | 4.71 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Construction of 2 nos. (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for 2nd and 3rd tubewell sites of KANNYANAGAR PIPE WATER SUPPLY SCHEME to accommodate FHTC in Bishnupur-I Block under South 24 Pgns. W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in Arsenic affected areas of South 24-Pgs. Dist. [SM/18574] | AE S24D1,AE SWSD-II | JE4 | ORD/000032/2025-2026 | 983/SWD-I | 09/04/2025 | 03/02/2026 | GLOBAL CONSTRUCTION | 11.5 | 0 | 0 | 98
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Payment of Quotation for new service connection at Kanyanagar PWSS PH No- 1 under Bishnupur-I Block. Application No- 1008452218 Reference ID- 107000243 |  |  | BILL/00106/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 17.43 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Pyment of Quotation for new service connection at Kanyanagar PWSS PH No- 3 under Bishnupur-I Block. Application No- 1008493955 Reference ID- 107014413 |  |  | BILL/00105/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 12.19 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based KANYANAGAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affecte | SM/18574 | Augmentation | Payment of Quotation for new service connection at Kanyanagar PWSS PH No- 2 under Bishnupur-I Block. Application No- 1008439469 Reference ID- 106984473 Memo No- 1008439469/Quot/03 |  |  | BILL/00362/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 4.75 | 0 | 0 | 0
Total | [13 empty] | 1400.53 | 2.92 | 0.21