## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18656 | Augmentation | Laying distribution system of piped water supply at Zone-VIII (Nimpith) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-2 | ORD/000454/2021-2022 | 2340/SWD-I | 22/02/2022 | 01/06/2026 | K P CONSTRUCTION | 432.84 | 238.27 | 55.05 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18656 | Augmentation | Balance civil works of Jaynagar-II GLR (Nimpith) under "Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas." under Baruipur Sub-Division of South 24-Parganas Water Supply Division-I, PHE Dte. | AE BSD | JE-2 | ORD/000018/2022-2023 | 875/SWD-I | 14/07/2022 | 28/02/2025 | MALLICK ENTERPRISE | 92.73 | 49.63 | 53.53 | 60
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18656 | Augmentation | Construction of 1000 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap for " Augmentation of laying distribution system to extend the benifit of 100 % Household in ZONE-VIII at JAYNAGAR-II block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist. South 24 Parganas under South 24 Paraganas Water Supply Division-I Division of PHE Dte." (TSM/015336 ) | AE BSD | JE RWS,JE-2 | ORD/000432/2023-2024 | 2006/SWD-I | 28/08/2023 | 31/03/2025 | M/S. S.S. ENTERPRISE | 357.14 | 0 | 0 | 30
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18656 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 382/SWD-I | 27/04/2023 | 27/04/2023 | Resource Division | 126.39 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18656 | Augmentation | Construction of pipe carrying structure with laying of 610 mm dia M.S. Secondary Rising Main for crossing of Canal at Bakultala Natunhaater Culvert and Nimpith Tulsighata Bridge under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/18656] | AE BSD | JE-2 | ORD/000284/2024-2025 | 3040/SWD-I | 02/07/2024 | 01/08/2024 | SRIJON ENTERPRISE | 45.72 | 5.31 | 11.61 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18656 | Augmentation | Laying of 610 mm dia M.S. pipe line for connecting gaps of Secondary grid at both ends of Nimpith Tulsighata bridge under Augmentation of laying distribution system to extend the benefit of 100% Household in Zone-VIII at Joynagar-II block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns. under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/18656) | AE BSD | JE RWS,JE-2 | ORD/000567/2024-2025 | 4240/SWD-I | 30/09/2024 | 14/11/2024 | SRIJON ENTERPRISE | 15.87 | 0 | 0 | 99
Total | [13 empty] | 1070.68 | 293.21 | 27.39