## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18677 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Baharu Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000969/2022-2023 | 1386/SWD-I | 20/09/2022 | 20/10/2022 | MEASURE LAND | 2.91 | 2.89 | 99.3 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18677 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of BAHARU MOUZA of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4292] [TSM/017335] | AE BSD | JE-2 | ORD/000408/2023-2024 | 1925/SWD-I | 22/08/2023 | 20/11/2023 | M/S G. C. CONSTRUCTION | 530.53 | 331.85 | 62.55 | 60
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18677 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Baharu water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/001634/2023-2024 | 2945/SMD | 05/09/2023 | 05/12/2023 | DAS ENTERPRISE | 35.08 | 10.63 | 30.3 | 30
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18677 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BAHARU PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017335] | AE BSD | JE-2 | ORD/000365/2023-2024 | 1774/SWD-I | 11/08/2023 | 10/09/2023 | MATRI ENTERPRISE | 47.62 | 45.92 | 96.43 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18677 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 99.15 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18677 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Baharu W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | Assistant Engineer | Junior Engineer | ORD/002479/2024-2025 | 434/SMSD | 09/04/2024 | 24/04/2024 | DAS ENTERPRISE | 0.63 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18677 | Augmentation | Construction of Platform for providing FHTC, approach road, protection work for pipeline and other allied works for Ground water based BAHARU piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/18677) [2nd call] | AE BSD | JE-2 | ORD/000546/2024-2025 | 4134/SWD-I | 23/09/2024 | 18/09/2025 | RANADHIR SINHA | 94.75 | 0 | 0 | 30
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18677 | Augmentation | Construction of 02 (two) nos. chlorination rooms for BAHARU Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I Block under South 24-Pgns. W/S Divn.-I, PHE Dte., South 24-Pgs. Dist. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/18677) | AE BSD | JE-2 | ORD/001127/2024-2025 | 190/SWD-I | 17/01/2025 | 13/11/2025 | S.M. ENTERPRISE (MOGRAHAT) | 11.41 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BAHARU piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18677 | Augmentation | Quotation for new power connection at P.H. NO.2 of Baharu w/s scheme . Application No. : 1009273564 . Reference Id : 107504299 . |  |  | BILL/00781/2026-2027 |  | 08/07/2026 | 08/07/2026 | WBSEDCL | 3.85 | 0 | 0 | 0
Total | [13 empty] | 825.93 | 391.28 | 47.37