## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/18678 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Bishweshwarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000753/2023-2024 | 2684/SMD | 16/08/2023 | 14/11/2023 | WEST BENGAL ENGINEERING CO. | 23.38 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/18678 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 3395/SWD-I | 10/03/2023 | 10/03/2023 | Resource Division | 15.58 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/18678 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 2414/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 32.9 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/18678 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BISHWESHWAR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017284] | AE BSD,AE S24D1,AE SWSD-II | JE3 | ORD/000364/2023-2024 | 1773/SWD-I | 11/08/2023 | 10/09/2023 | JYOTY SOLAR POWER (EMAIL ID-INFO.JYOTYSOLARPOWER@GMAIL.COM) | 31.79 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/18678 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Bishweshwarpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000981/2022-2023 | 1455/SWD-I | 26/09/2022 | 26/10/2022 | GEO SOLUTION | 2.8 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/18678 | Augmentation | Quotation for new service connection at PH NO.1 of Biseswarpur w/s scheme . Application no.1008233157 . |  |  | BILL/02235/2024-2025 | BP-2024-25-496 | 19/12/2024 | 19/12/2024 | WBSEDCL | 5.53 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/18678 | Augmentation | Construction of 01 (one) no. 350 Cum capacity 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 02 (two) nos. chlorination room of size 5.0m x 4.0m for BISHWESHWARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 2530] [TSM/017284] | AE S24D1,AE SWSD-II | JE3 | ORD/000507/2023-2024 | 2221/SWD-I | 12/09/2023 | 01/04/2026 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 646.17 | 0 | 0 | 45
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/18678 | Augmentation | Construction of Boundary wall, FHTC Platform, approach road, land development, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of aurface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/18678) | AE S24D1,AE SWSD-II | JE3 | ORD/000384/2024-2025 | 3575/SWD-I | 12/08/2024 | 11/02/2026 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 241.51 | 0 | 0 | 15
Total | [13 empty] | 999.67 | 0 | 0