## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based ANDHARMANIK piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/18680 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Andharmanik water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000754/2023-2024 | 2685/SMD | 16/08/2023 | 14/11/2023 | NUPUR CHANDRA HALDER | 22.36 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ANDHARMANIK piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/18680 | Augmentation | Preparation and submission of Detailed Project Report of ANDHARMANIK AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000463/2021-2022 | 1975/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 3.1 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ANDHARMANIK piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/18680 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 323/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 23.18 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ANDHARMANIK piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/18680 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for ANDHARMANIK PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 3023) [TSM/016562]. | AE SWSD-II | JE3 | ORD/000410/2023-2024 | 1937/SWD-I | 22/08/2023 | 20/11/2023 | TARUN ENTERPRISE | 475.56 | 0 | 0 | 40
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ANDHARMANIK piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/18680 | Augmentation | Laying rising main and additional pipeline for distribution system, construction of boundary wall, approach road, pipeline protection, land development and road restoration for ANDHARMANIK PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/18680) | AE SWSD-II | JE3 | ORD/000371/2024-2025 | 3530/SWD-I | 07/08/2024 | 15/01/2026 | J. D. ENTERPRISE | 204.18 | 0 | 0 | 20
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ANDHARMANIK piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/18680 | Augmentation | Construction of 4 (four) nos pipe carrying structures including laying of 150mm dia M.S. distribution Pipe at Node Point 71-101 (27.50mtr), 100mm M.S. distribution Pipe at Node Point 107-111 (44.00mtr) and 80mm M.S. distribution Pipe at Node Point 302-310 (22.00mtr) & Node Point 214-215 (16.50mtr) over Nepalgaunge-Julpia canal and 2 (two) nos Culvert crossing by laying of 150mm dia M.S distribution Pipe at Node point 358-359 (11.00mtr) & Node point 358-359 (11.00mtr) for ANDHARMANIK PIPE WATER SUPPLY SCHEME to accommodate FHTC in Bishnupur-I Block under South 24-Pgns. W/S Divn.-I, PHE Dte. for Augmentation of surface water based water supply scheme in arsenic affected areas of South 24 Parganas District. [SM/18680] |  |  | ORD/000127/2025-2026 | 1782/SWD-I | 02/07/2025 | 31/08/2025 | SRIJON ENTERPRISE | 24.53 | 0 | 0 | 0
Total | [13 empty] | 752.92 | 0 | 0