## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of BHANDARIA PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/017323] (2nd call) | AE SWSD-II |  | ORD/000383/2023-2024 | 1819/SWD-I | 16/08/2023 | 15/10/2023 | KAMALA TRADING COMPANY | 17.64 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3&4, of Bhandaria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000755/2023-2024 | 2686/SMD | 16/08/2023 | 14/11/2023 | MAHADEV ENTERPRISE | 52.04 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Bhandaria Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000955/2022-2023 | 1130/SWD-I | 24/08/2022 | 23/09/2022 | GEO SOLUTION | 2.89 | 2.87 | 99.34 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 323/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 58.78 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Payment for initial 50% amount of the estimated cost Rs 3983175.00(Rupees thirty nine lakh eighty three thousand one hundred seventy five only) i.e. Rs 1991587.50 round off Rs 1991588.00( Rupees nineteen lakh ninety one thousand five hundred eighty eight only) toward road restoration work of Pailan Nepalgunj (ch from 0.00 km to 1.450 km, left hand side) Road under Doulatpur & Kastamahal Pipe Water Supply Scheme in Bishnupur-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. |  |  | BILL/00347/2024-2025 | BP-2024-25-243 | 08/08/2024 | 08/08/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 19.92 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Payment for quotation for new service connection at Bhandaria PWSS, PH No. - I (JL No- 142, Mouza- Chamni) Application No- 1008184995 Reference ID- 106819600 Memo No- 1008184995/Quot/03/945 Quotation Date- 14-11-2024 |  |  | BILL/01897/2024-2025 | BP-2024-25-480 | 28/11/2024 | 28/11/2024 | WBSEDCL | 3.89 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Payment of Quotation for new service connection at Bhandaria PWSS PH No- 3 under Bishnupur-I Block. Application No- 1008242098 Application Date- 09-12-2024 Reference ID- 106856036 Memo No- 1008242098/Quot/03 |  |  | BILL/02239/2024-2025 | BP-2024-25-495 | 19/12/2024 | 19/12/2024 | WBSEDCL | 6.08 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for Proposed BHANDARIA PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 3721] | AE SWSD-II | JE1 | ORD/000406/2023-2024 | 1923/SWD-I | 22/08/2023 | 16/12/2025 | M/S. S.S. ENTERPRISE | 482.45 | 321.65 | 66.67 | 78
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Construction of temporary approach road and land development for the 2nd Tubewell site of Bhandaria PWSS of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District [SM/18681] |  |  | ORD/001081/2024-2025 | 5348/SWD-I | 30/12/2024 | 29/01/2025 | MD RUHUL AMIN GOLDER | 7.8 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Laying Rising Main and additional pipeline as per revised design and drawing of distribution system for BHANDARIA piped water supply scheme to accommodate FHTC in Bishnupur-I block under South 24 Pgs W/S Division-I, South 24-Pgns District for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Pgns. District. (SM/18681) | AE SWSD-II | JE1 | ORD/000263/2024-2025 | 2678/SWD-I | 07/06/2024 | 09/12/2025 | M/S. S.S. ENTERPRISE (NODAKHALI) | 91.24 | 27.15 | 29.76 | 65
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Construction of 02 nos. pump houses, approach road, land development and pipeline protection of rising and distribution system for BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24-Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/18681) | AE SWSD-II | JE1 | ORD/000272/2024-2025 | 2922/SWD-I | 25/06/2024 | 15/02/2026 | M/S. S.S. ENTERPRISE (NODAKHALI) | 76.09 | 8.86 | 11.65 | 22
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Construction of Boundary wall for 2nd & 3rd T/W site for BHANDARIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas for Augmentation of Surface Water Based Water Supply Sheme in the Arsenic affected areas of South 24 Parganas District. (51 mtr. For each site) [SM/18681] | AE S24D1 | JE1 | ORD/000262/2024-2025 | 2677/SWD-I | 07/06/2024 | 13/11/2025 | S.P. ENTERPRISE | 13.56 | 0 | 0 | 93
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BHANDARIA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017323] | AE SWSD-II | JE1 | ORD/000378/2023-2024 | 1812/SWD-I | 16/08/2023 | 30/11/2024 | MD RUHUL AMIN GOLDER | 15.89 | 4.09 | 25.72 | 98
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/18681 | Augmentation | Sinking of 02 (Two) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd and 3rd tubewell site for BHANDARIA Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/18681) | AE SWSD-II | JE1 | ORD/000687/2024-2025 | 4482/SWD-I | 30/10/2024 | 31/01/2025 | MONDAL TUBEWELL | 31.71 | 0 | 0 | 50
Total | [13 empty] | 879.98 | 364.62 | 41.44