## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Carriage of K9 DI pipes of various diameters from Dongaria WTP PHE stores to work site at Mandirbazar for laying of Secondary Grid pipeline within Mandirbazar Block under the Augmentation of LDS to extend the benefit of 100% households in Zone-I at Mandirbazar Block within the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas¿ under South 24 Parganas Water Supply Division-I, PHE Dte. (SM/18706) |  |  | ORD/000662/2023-2024 | 2958/SWD-I | 24/11/2023 | 01/12/2023 | M/S SHIBAM ENTERPRISE | 1.24 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Laying of 600 mm dia MS Secondary Grid Pipe from Mandirbazar GLR-Pump House to 600mm Dia DI Secondary Grid Pipeline under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist.- South 24-Pgns.Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-I at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (SM/018706) | AE HQ-I | JE-3 | ORD/000549/2023-2024 | 2497/SWD-I | 06/10/2023 | 05/11/2023 | S. ROY AND ASSOCIATES | 4.91 | 4.9 | 99.72 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Construction of boundary wall for proposed OHR Site of Zone-I within Mandirbazar block, Mouza-Mallik Protap under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 200.6 mtr.) under South 24-Pgns. W/S Division-I, PHE Dte. |  |  | ORD/000566/2021-2022 | 2694/SWD-I | 25/03/2022 | 23/06/2022 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD. | 26.82 | 6.33 | 23.59 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of MALLICKPRATAP MOUZA in MANDIRBAZAR (ZONE-I) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. |  |  | ORD/000512/2021-2022 | 1983/SWD-I | 27/01/2022 | 26/02/2022 | RADIANT | 4.83 | 4.17 | 86.26 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 3016/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 276.01 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Road Restoration and Horizontal Boring for laying of Secondary Grid within Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-I at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte.(TSM/014517) | AE HQ-II | JE-3 | ORD/000398/2023-2024 | 1891/SWD-I | 18/08/2023 | 02/10/2023 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 7.01 | 3.9 | 55.58 | 50
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Three months trial run for secondary grid D.I pipe lines of different diameters of Mandirbazar Block within Mega surface water based water supply scheme of Falta-Mathurapur District South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/18706) |  |  | ORD/000873/2024-2025 | 4931/SWD-I | 03/12/2024 | 17/01/2025 | M/S. GOUTAM ROY | 16.98 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Gap Negotiation for secondary grid of Mandirbazar Block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/18706] |  |  | ORD/000697/2024-2025 | 4499/SWD-I | 30/10/2024 | 29/12/2024 | S. ROY AND ASSOCIATES | 56.45 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Diversion of Water for "Construction of Hume Pipe Culvert infront of 10.00 Mtr span for proposed Zone-I OHR Site at Mallick Pratap Mouza (J.L.NO-02, Plot No-964) at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-I at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/18706) | AE HQ-I | JE-3 | ORD/000433/2024-2025 | 3875/SWD-I | 03/09/2024 | 03/10/2024 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 4.68 | 4.63 | 98.88 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-I at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9379) | AE HQ-I | JE-3 | ORD/000423/2023-2024 | 1970/SWD-I | 24/08/2023 | 21/07/2026 | MAA MANASA VYAPAAR | 1837.75 | 437.71 | 23.82 | 5
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Development of land and construction of approach road for Head Work site (Zone I) at Mallick Pratap Mouja (J.L. No 02) at Mandirbazar Block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under SWD-I, PHE Dte. (SM/18706) |  |  | ORD/000416/2024-2025 | 3736/SWD-I | 27/08/2024 | 11/10/2024 | MAA MANASA VYAPAAR | 20.12 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-I AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18706 | Augmentation | Construction of Hume Pipe Culvert of 10.00Mtr.span for proposed Zone-I OHR Site at Mallick Pratap Mouza(J.L.NO-02,Plot No-964) at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-I at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/014517) | AE HQ-I | JE-3 | ORD/000380/2023-2024 | 1816/SWD-I | 16/08/2023 | 09/12/2024 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD | 16.11 | 0 | 0 | 75
Total | [13 empty] | 2272.91 | 461.63 | 20.31