## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South | SM/18708 | Augmentation | Supplying, fabrication & laying of 700 mm dia (ID) MS Pipe conduits 72 mtr. in length to be prepared from 12 mm thick MS Plate by pipe jacking technique, including supplying and laying of 250 mm dia (ID) MS water supply pipe line within the conduit 90 mtr. in length to be prepared from 06 mm thick MS Plate across and underneath the Railway Track in between mast no-50/11, 50/13 and mast no-50/12, 56/14 in between Deula Station and Netra Stations on Baruipur - Diamond Harbour Section as per permission obtained from Railway Authority, including construction of Drive Pit & Receiving Pit, as requred, for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-VI at Mograhat-I Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/03906) | AE SWSD-II | JE4 | ORD/000499/2022-2023 | 2868/SWD-I | 09/02/2023 | 10/04/2023 | S. ROY AND ASSOCIATES | 76.87 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South | SM/18708 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 284/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 8.27 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South | SM/18708 | Augmentation | Construction of boundary wall & other allied works at Head Work in Zone-VI at Ektara of Mograhat-I block for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI AT EKTARA OF MOGRAHAT-I BLOCK within "Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, District- South 24-Parganas" under South 24 Parganas W/S Division-I, PHE Dte. (Total Length-112 mtr excluding Gate) (TSM/014910) | AE SWSD-II | JE2 | ORD/000352/2023-2024 | 1738/SWD-I | 10/08/2023 | 09/10/2023 | NIKHIL SAMADDAR | 18.85 | 0 | 0 | 1
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South | SM/18708 | Augmentation | Construction of Platform for FHTC, Additional pipelines for distribution system, Protection of pipeline, Approach road and construction of Chlorination Room for Augmentation of existing laying distribution system and allied works to extend the benifit of 100% Household in Zone-VI at Ektara under Magrahat-I Block within Mega surface Water based water supply scheme of Falta-Mathurapur,Dist. S-24 pgns under South 24 parganas W/S Division-I, P.H.E Dte. (SM/18708) | AE SWSD-II | JE2 | ORD/000537/2024-2025 | 4093/SWD-I | 20/09/2024 | 19/12/2024 | CONCORD ENGINEERING | 319.66 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South | SM/18708 | Augmentation | Land development at Head Work site of EKTARA ZONE-VI PWSS under Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Pgns. under South 24-Pgns W/S Divn-I, PHE Dte. (SM/18708) | AE SWSD-II | JE2 | ORD/000412/2024-2025 | 3713/SWD-I | 23/08/2024 | 07/10/2024 | TIYASHA ENTERPRISE | 20.8 | 0 | 0 | 1
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South | SM/18708 | Augmentation | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-VI at EKTARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VI at EKTARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 9230 Nos.) | AE SWSD-II | JE2 | ORD/000373/2023-2024 | 1782/SWD-I | 11/08/2023 | 06/06/2024 | CONCORD ENGINEERING | 1862.26 | 0 | 0 | 55
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South | SM/18708 | Augmentation | Construction of Balance portion of Boundary Wall for EKTARA ZONE-VI PWSS under Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Pgns. under South 24-Pgns W/S Divn-I, PHE Dte. (SM/18708) [2nd call] | AE SWSD-II | JE2 | ORD/001119/2024-2025 | 155/SWD-I | 15/01/2025 | 14/02/2025 | NIKHIL SAMADDAR | 12.03 | 0 | 0 | 0
Total | [13 empty] | 2318.75 | 0 | 0