## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Construction of Boundary wall for proposed 500 Cum OHR Site of Zone-V within Mandirbazar block, Mouza-PurbaShrinagar (JL No-98), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 135 mtr.) | AE HQ-I | JE-3 | ORD/000021/2022-2023 | 876/SWD-I | 14/07/2022 | 12/09/2022 | MS P B CONSTRUCTION | 25.37 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of PURBA SRINAGAR MOUZA in MANDIRBAZAR (ZONE-V) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000462/2021-2022 | 1987/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 4.42 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 3016/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 58.22 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Construction of Hume Pipe Culvert 4.80 Mtr.span with 195 Mtr.Long temporary approach road(Plot No-183,189,189) for proposed Zone -V,OHR Site at Purba Srinagar Mouza(J.L.NO-98,Dag No-80,Khatian No-(60,147&256).at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/014532) | AE HQ-I | JE-3 | ORD/000381/2023-2024 | 1817/SWD-I | 16/08/2023 | 05/01/2025 | M/S. KALPANA CONSTRUCTION | 13.51 | 0 | 0 | 60
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Diversion of Water for "Construction of Hume Pipe Culvert of 10.00 Mtr span for proposed Zone-V OHR Site at Purba Shreenagar Mouza (J.L.NO-132) at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-V at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/18715) | AE HQ-I,Assistant Engineer | JE-3,JE2 | ORD/000432/2024-2025 | 3874/SWD-I | 03/09/2024 | 03/10/2024 | M/S. KALPANA CONSTRUCTION | 6.06 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Road restoration for L036- Gabbria on T01 to Purba paschima para (WB02 403) |  |  | BILL/01735/2024-2025 | BP-2024-25-799 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 5.64 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Lakshmikantapur Dhola Road from 1.00KM to 2.00km Restoration of hard shoulder due to laying of pipelinesby PHE Department under Lakshmikantapur Highway Sub Division in the district of South 24 Parganas. (SM/18715) |  |  | BILL/00634/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 4.47 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Construction of 500 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.3829) | AE HQ-I | JE-3 | ORD/000461/2023-2024 | 2139/SWD-I | 31/08/2023 | 19/10/2025 | BALAJEE ENTERPRISES | 760.19 | 0 | 0 | 75
Total | [13 empty] | 877.87 | 0 | 0