## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying Distribution, Rising Main, Functional Household Tap Connection (FHTC) for Augmentation of HARIHARPUR (PART-II) of Baruipur Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24-Parganas District [No. of FHTC = 1763] | AE BSD | JE-1 | ORD/000566/2023-2024 | 2639/SWD-I | 20/10/2023 | 26/03/2025 | MODERN CONSTRUCTION (MURSHIDABAD) | 216.74 | 18.94 | 8.74 | 60
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Sinking of 04 (four) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for HARIHARPUR (Part-II) PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/18869] | AE BSD | JE-1 | ORD/000714/2023-2024 | 3430/SWD-I | 29/12/2023 | 12/02/2024 | PADMA ENGINEERING CO. | 63.59 | 32.18 | 50.61 | 75
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Hariharpur ( Part-II ) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000166/2024-2025 | 2124/SMD | 12/07/2024 | 01/08/2025 | KARUNAMOY ENGINEERING | 12.62 | 11.74 | 93.02 | 80
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 4 for Hariharpur ( Part-II ) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000222/2024-2025 | 2453/SMD | 01/08/2024 | 30/10/2024 | SAIKAT ENTERPRISE | 12.62 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 for Hariharpur ( Part-II ) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000171/2024-2025 | 2305/SMD | 22/07/2024 | 20/10/2024 | P.P. CONCERN | 12.57 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Construction of platfrom for FHTC, restoration of road, Protection of Pipeline and other allied works for "Ground Water Based Hariharpur(Part-II) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/18869) |  |  | ORD/000522/2024-2025 | 4015/SWD-I | 13/09/2024 | 12/11/2024 | MODERN CONSTRUCTION (MURSHIDABAD) | 79.26 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 for Hariharpur ( Part-II ) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000223/2024-2025 | 2454/SMD | 01/08/2024 | 30/10/2024 | RMD TRADING | 12.76 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Charges for new service connection at Pump house no-3 of Hariharpur (Part-II) water supply scheme (Baruipur Block) |  |  | BILL/01803/2024-2025 | BP-2024-25-439 | 07/10/2024 | 07/10/2024 | WBSEDCL | 14.09 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Charges for New service connection at Pump house no-2 of Hariharpur (Part-II) water supply scheme (Baruipur Block) |  |  | BILL/01802/2024-2025 | BP-2024-25-438 | 07/10/2024 | 07/10/2024 | WBSEDCL | 3.75 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HARIHARPUR (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of | SM/18869 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04084/2023-2024 | BP-2023-24-415 | 16/12/2023 | 16/12/2023 | WBSEDCL | 2.61 | 0 | 0 | 0
Total | [13 empty] | 430.6 | 62.86 | 14.6