## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandpur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000244/2020-2021 | 1443/MD | 26/11/2020 | 25/05/2021 | MASUM ALI KHAN | 76.1 | 135.99 | 178.69 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandpur W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000746/2020-2021 |  | 15/12/2020 | 15/12/2020 | MASUM ALI KHAN | 30 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000762/2021-2022 | 8443212 | 27/09/2021 | 27/09/2021 | SIDDHESWAR BAG | 0.17 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000760/2021-2022 | 8443212 | 27/09/2021 | 27/09/2021 | MANABENDRA DAS | 0.14 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000761/2021-2022 | 8443212 | 27/09/2021 | 27/09/2021 | RINTU SAMANTA | 0.12 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | FHTC data entry. |  |  | VCH/001204/2021-2022 | 844334 | 08/12/2021 | 08/12/2021 | SIDDHESWAR BAG | 0.14 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | FHTC data entry. |  |  | VCH/001203/2021-2022 | 844334 | 08/12/2021 | 08/12/2021 | MANABENDRA DAS | 0.14 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | FHTC Data Entry. |  |  | VCH/001280/2021-2022 | 844361 | 18/01/2022 | 18/01/2022 | GANESH CH NANDY | 0.2 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | FHTC data Entry. |  |  | VCH/001281/2021-2022 | 844361 | 18/01/2022 | 18/01/2022 | SUBRATA CHAKRABORTY | 0.12 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | Engagement of 1(one) no Contractual Clerical staff cum office assistant for different official purpose for office of the Assistant Engineer, Ghatal Sub-Division, P.H.E. dte. (1st year) |  |  | VCH/000995/2022-2023 | 844356 | 09/09/2022 | 09/09/2022 | DEVJYOTI BERA | 0.18 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chandpur Piped Water Supply Scheme. | SM/06894 | Retrofitting | Engagement of 1 (One) No. Orderly Peon,Contractrual Group-D, through Agency for different official purpose for office of the office of the Assistant Engineer, Ghatal Sub-Division, P.H.E. Dte. (For 12 months) |  |  | VCH/000986/2022-2023 | 8443171 | 26/09/2022 | 26/09/2022 | SUBHASIS DOLAI | 0.16 | 0 | 0 | 0
Total | [13 empty] | 107.46 | 135.99 | 126.55