## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Maligram Piped Water Supply Scheme. | SM/06895 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Maligram PWSS, Block: - Pingla, in the District of Paschim Medinipur. |  |  | VCH/001308/2021-2022 | 844397 | 25/01/2022 | 25/01/2022 | UTTAM KUMAR DAS | 17.78 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Maligram Piped Water Supply Scheme. | SM/06895 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Maligram PWSS, Block: - Pingla, in the District of Paschim Medinipur. |  |  | VCH/001476/2021-2022 | 844397 | 25/01/2022 | 25/01/2022 | UTTAM KUMAR DAS | 14.42 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Maligram Piped Water Supply Scheme. | SM/06895 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maligram W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000254/2020-2021 | 1450/MD | 26/11/2020 | 25/05/2021 | HARIPADA PATTANAYAK | 96.05 | 35.03 | 36.47 | 96
Total | [13 empty] | 128.25 | 35.03 | 27.32