## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maliara W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000715/2020-2021 |  | 15/12/2020 | 15/12/2020 | M/S. EL-CON | 27.28 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Sinking of One no Additional Rig bored Tube Well 150 X 100 mm dia. X 120 Mtr. Depth for Maliara Pipe W/S Scheme under Midnapur Sadar Sub Division Within Midnapore Division, PHE Dte. (SL No-01) | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000286/2022-2023 | 464./AE/MSSD | 08/08/2022 | 18/08/2022 | HIRAK KUMAR GHOSH | 4.74 | 4.58 | 96.56 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maliara W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division |  | ORD/000203/2020-2021 | 1426/MD | 26/11/2020 | 25/05/2021 | M/S. EL-CON | 40.92 | 54.97 | 134.34 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Additional Laying of Distribution pipe line at (Kalgunj ,Madhypara, Gourangapally & other different left out area) within Maliara Pipe Water Supply Scheme under Medinipore Sadar Block within Midnapore Division ,PHE Dte. (SL No-01) | AE/RWS Midnapore Sub Division |  | ORD/000215/2023-2024 | 481/AE/MSSD | 08/08/2023 | 18/08/2023 | HIRAK KUMAR GHOSH | 4.18 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Continuation for the work of "Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre , Health Care Institution etc" under Midnapur Division,PHE Dte. for the period of 03 months (from 01.04.2022 to 30.06.2022) |  |  | ORD/001014/2021-2022 | 147/AE/MSSD | 28/03/2022 | 31/03/2022 | PULLOCK KUMAR GHOSH | 1.52 | 1.52 | 100 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Maliara water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002150/2022-2023 | 1345/MMSD-I | 30/12/2022 | 14/01/2023 | P.K.ENGINEERING | 4.37 | 4.37 | 100 | 100
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Electric Bill of WBSEDCL. |  |  | BILL/00732/2022-2023 | BP-2022-23-683 | 09/03/2023 | 09/03/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.19 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Quotation as per WBSEDCL procedure-A (2010) electric quotation bill. |  |  | BILL/00412/2022-2023 | BP-2022-23-683 | 09/03/2023 | 09/03/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.19 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Accommodate FHTC( 70 ) including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Maliara Water Supply Scheme within Medinipur Sadar Dev. Block under Midnapur Sadar Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. (SL No-02) | AE/RWS Midnapore Sub Division |  | ORD/000221/2023-2024 | 482/AEMSSD | 08/08/2023 | 18/08/2023 | HIRAK KUMAR GHOSH | 4.44 | 2.33 | 52.49 | 100
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Maliara PWSS | SM/06898 | Retrofitting | Accommodate FHTC( 70 ) including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Maliara Water Supply Scheme within Medinipur Sadar Dev. Block under Midnapur Sadar Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. (SL No-02) |  |  | BILL/02171/2023-2024 | BP-2023-24-601 | 02/02/2024 | 02/02/2024 | HIRAK KUMAR GHOSH | 0.23 | 0 | 0 | 0
Total | [13 empty] | 88.06 | 67.76 | 76.95