## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. | SM/06899 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Harekrishnapur W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000740/2020-2021 |  | 15/12/2020 | 15/12/2020 | DIPAK KUMAR DOLAI | 98.16 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. | SM/06899 | Retrofitting | Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at The Head work site Midnapore Divison , PHE Dte. |  |  | BILL/00729/2022-2023 | 8443129 | 31/03/2023 | 31/03/2023 | M/S. OXFORD SECURITY SERVICE | 1.03 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. | SM/06899 | Retrofitting | Laying additional pipe line for retrofitting to accommodate FHTC under JJM in Harekrishnapur PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division PHE.Dte. (For the Villages- Mahabatpur, nabin Simla & Sridharpur) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000460/2020-2021 | 82/AE/GSD | 25/02/2021 | 17/03/2021 | SUBHASIS DOLAI | 4.78 | 9.63 | 201.57 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. | SM/06899 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in HAREKRISHNAPUR PWSS in Daspur-I Block in the District of Paschim Midnapore. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000655/2020-2021 | 450/MD | 26/02/2021 | 28/03/2021 | SUBHASIS DOLAI | 13.85 | 13.15 | 94.93 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Harekrishnapur Piped Water Supply Scheme. | SM/06899 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Harekrishnapur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000209/2020-2021 | 1430/MD | 26/11/2020 | 25/05/2021 | DIPAK KUMAR DOLAI | 94.96 | 70.49 | 74.23 | 0
Total | [13 empty] | 212.78 | 93.26 | 43.83