## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. | SM/06900 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Katan W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000248/2020-2021 | 1447/MD | 26/11/2020 | 25/05/2021 | SHAKEEL KHAN | 45.04 | 16.25 | 36.07 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. | SM/06900 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Katan W/S Scheme, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000759/2020-2021 |  | 15/12/2020 | 15/12/2020 | SHAKEEL KHAN | 30 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. | SM/06900 | Retrofitting | Restoration of road damaged during carrying of pipe line and allied works of KATAN water supply scheme within Ghatal Sub-Division under Midnapore Division, P.H.E. Dte. (Node- 102-105) | AE Ghatal Sub-division |  | ORD/000502/2021-2022 | 806/AE/GSD | 16/12/2021 | 26/12/2021 | DEVJYOTI BERA | 0.62 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. | SM/06900 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Katan W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/001369/2021-2022 | BP-2021-22-414 | 24/02/2022 | 24/02/2022 | SHAKEEL KHAN | 14.25 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. | SM/06900 | Retrofitting | Retrofitting to accommodate Additional FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Katan Water Supply Scheme (Paschim Para) within Ghatal Dev. Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000652/2022-2023 | 147/AE/GSD | 17/02/2023 | 19/03/2023 | DEVJYOTI BERA | 3.57 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Katan Piped Water Supply Scheme. | SM/06900 | Retrofitting | Retrofitting to accommodate Additional FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Katan Water Supply Scheme (Paschim Para) within Ghatal Dev. Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000766/2022-2023 | 149/AE/GSD | 21/02/2023 | 23/03/2023 | DEVJYOTI BERA | 3.57 | 0 | 0 | 10
Total | [13 empty] | 97.06 | 16.25 | 16.74