## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. | SM/06902 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khanjapur W/S Scheme, Block: - Daspur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000247/2020-2021 | 1446/MD | 26/11/2020 | 25/05/2021 | MIDNAPUR PIPE CONCERN | 48.96 | 26.1 | 53.3 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. | SM/06902 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khanjapur W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000751/2020-2021 | null | 15/12/2020 |  | MIDNAPUR PIPE CONCERN | 10 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. | SM/06902 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khanjapur W/S Scheme, Block: - Daspur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/001875/2021-2022 | 8443244 | 29/03/2022 |  | MIDNAPUR PIPE CONCERN | 10 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khanjapur Piped Water Supply Scheme. | SM/06902 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM in Khanjapur W/S Scheme, Block: - Daspur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000516/2022-2023 | 2534/MD | 12/12/2022 | 26/12/2022 | MIDNAPUR PIPE CONCERN | 7 | 4.95 | 70.73 | 50
Total | [13 empty] | 75.96 | 31.05 | 40.88