## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barisha (Zone-I) W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000273/2020-2021 | 1471/MD | 26/11/2020 | 25/05/2021 | SK. SALIM | 96.82 | 34.85 | 36 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000764/2021-2022 | 8443208 | 27/09/2021 | 27/09/2021 | SUBRATA CHAKRABORTY | 0.12 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000763/2021-2022 | 8443208 | 27/09/2021 | 27/09/2021 | PAPPU SHAW | 0.2 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | Retrofitting to accomdate 80(Eighty) nos FHTC under JJM at different places for Barisha (Zone -I) and its adjoining Mouzas Water Supply Scheme Within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000001/2022-2023 | 213/AE/KSD | 29/04/2022 | 14/05/2022 | SK. TASLIM | 4.82 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | FHTC data entry. |  |  | VCH/001205/2021-2022 | 844337 | 08/12/2021 | 08/12/2021 | GANESH CH NANDY | 0.11 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | FHTC data entry. |  |  | VCH/001206/2021-2022 | 844337 | 08/12/2021 | 08/12/2021 | PAPPU SHAW | 0.12 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | FHTC Data Entry. |  |  | VCH/001279/2021-2022 | 844360 | 18/01/2022 | 18/01/2022 | SIDDHESWAR BAG | 0.21 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | FHTC Data Entry. |  |  | VCH/001278/2021-2022 | 844360 | 18/01/2022 | 18/01/2022 | PAPPU SHAW | 0.17 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | FHTC data entry. |  |  | VCH/001207/2021-2022 | 844337 | 08/12/2021 | 08/12/2021 | SUBRATA CHAKRABORTY | 0.07 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | Laying of UPVC (Class-III) pipe line supportive to retrofitting to accommodate FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM at Barisha (Zone-I) and its adjoining mouza Water Supply Scheme within Pingla Dev. Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000482/2022-2023 | 2278/MD | 09/11/2022 | 30/11/2022 | AJIJUR RAHAMAN MALLICK | 10.96 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000106/2024-2025 | 3407/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.53 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-I) PWSS | SM/06903 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM at different places for Barisha (Zone-I) & its adj. mouzas W/S Scheme within Pingla block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000020/2022-2023 | 617/MD | 04/04/2022 | 01/01/2025 | NUTAN BAZAR ENGINEER,S CO-OPERATIVE SOCIETY LTD. | 39.19 | 0 | 0 | 100
Total | [13 empty] | 165.31 | 34.85 | 21.08