## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | FHTC Data entry |  |  | VCH/000626/2021-2022 | 8443119 | 23/08/2021 | 23/08/2021 | SIDDHESWAR BAG | 0.05 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Electric bill for the office of the Executive Engineer Mid. Mech. Divn. PHE Dte. |  |  | VCH/001061/2021-2022 | 844382 | 25/11/2021 | 25/11/2021 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.11 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | DATA ENTRY FOR FHTC |  |  | VCH/000835/2021-2022 | 844387 | 13/09/2021 | 13/09/2021 | MANABENDRA DAS | 0.08 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | FHTC Data entry |  |  | VCH/000625/2021-2022 | 8443119 | 23/08/2021 | 23/08/2021 | PAPPU SHAW | 0.04 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | DATA ENTRY FOR FHTC |  |  | VCH/000834/2021-2022 | 844387 | 13/09/2021 | 13/09/2021 | KOUSHIK PAL | 0.01 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | DATA ENTRY FOR FHTC |  |  | VCH/000839/2021-2022 | 844387 | 13/09/2021 | 13/09/2021 | BIPLAB SHIT | 0.01 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Electric bill for the office of the Executive Engineer Mid. Mech. Divn. PHE Dte. |  |  | VCH/001059/2021-2022 | 844383 | 25/11/2021 | 25/11/2021 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.11 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | FHTC Data entry |  |  | VCH/000627/2021-2022 | 8443119 | 23/08/2021 | 23/08/2021 | SUBRATA CHAKRABORTY | 0.03 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Electric bill for the office of the Executive Engineer Mid. Mech. Divn. PHE Dte. |  |  | VCH/001060/2021-2022 | 844381 | 25/11/2021 | 25/11/2021 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.11 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Milan Jana |  |  | VCH/000875/2021-2022 | 844387 | 19/09/2021 | 19/09/2021 | MILAN JANA | 0.01 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | DATA ENTRY FOR FHTC |  |  | VCH/000833/2021-2022 | 844387 | 13/09/2021 | 13/09/2021 | ANKITA HAZRA | 0.01 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | DATA ENTRY FOR FHTC |  |  | VCH/000841/2021-2022 | 844387 | 13/09/2021 | 13/09/2021 | SANJOY DAS | 0.02 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | FHTC imis data entry. |  |  | VCH/001642/2021-2022 | 8443146 | 24/03/2022 | 24/03/2022 | SOVANDEB MANNA | 0.09 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | FHTC imis data entry. |  |  | VCH/001639/2021-2022 | 8443146 | 24/03/2022 | 24/03/2022 | GANESH CH NANDY | 0.14 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | FHTC imis data entry. |  |  | VCH/001641/2021-2022 | 8443146 | 24/03/2022 | 24/03/2022 | RAJIB DEY | 0.15 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-I) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000233/2020-2021 | 1438/MD | 26/11/2020 | 25/05/2021 | M/S. EL-CON | 91.85 | 24.91 | 27.12 | 100
17 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Damage of existing pipeline lies under the existing carriageway of the road at Chuasol (Zone ¿V) & Boylasole ,Siarboni (zone) under Dherua and its adjoining mouzas water supply scheme within Midnapore Sadar Sub-Division under Midnapore Division PHE Dte. | AE Sadar Sub-division |  | ORD/000618/2022-2023 | 785/AE/MSSD | 06/01/2023 | 05/02/2023 | SANJIT SINHA | 1.78 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at The Head work site Midnapore Divison , PHE Dte. |  |  | BILL/00728/2022-2023 | 8443125 | 29/03/2023 | 29/03/2023 | M/S. OXFORD SECURITY SERVICE | 3.28 | 0 | 0 | 0
19 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre ,Health Care Institution etc. under Midnapore Division PHE Dte.(SL No-02) |  |  | ORD/000708/2020-2021 | 13/AE/MSSD | 06/01/2021 | 09/01/2021 | PULLOCK KUMAR GHOSH | 1.48 | 1.47 | 99.01 | 0
20 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Laying Distribution system connected with newly sunk tube well from Debra to Chuasole pipe line at Dherua Zone - IV piped water supply scheme with in Midnapore Sadar Block( Within MSSD) under Midnapore Division PHE Dte.(SL No-03) |  |  | BILL/00976/2024-2025 | 844357 | 24/10/2024 | 24/10/2024 | SANJIT SINHA | 1.48 | 0 | 0 | 0
21 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Laying Distribution system connected with newly sunk tube well from Chaipur Sitala Mandir to Kundalboni pipe line at Dherua Zone -I piped water supply scheme with in Midnapore Sadar Block ( Within MSSD) under Midnapore Division PHE Dte.(SL No-01) |  |  | BILL/00667/2024-2025 | 844334 | 09/05/2024 | 09/05/2024 | SANJIT SINHA | 2.7 | 0 | 0 | 0
22 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-I) PWSS | SM/06904 | Retrofitting | Laying Distribution system connected with newly sunk tube well from Mohulboni to Chaipur Sitala Mandir pipe line at Dherua Zone -I piped water supply scheme with in Midnapore Sadar Block( Within MSSD) under Midnapore Division PHE Dte.(SL No-02) |  |  | BILL/00711/2024-2025 | 844376 | 24/06/2024 | 24/06/2024 | SANJIT SINHA | 3.47 | 0 | 0 | 0
Total | [13 empty] | 106.99 | 26.37 | 24.65