## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | SM/06905 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mohanpur W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000246/2020-2021 | 1445/MD | 26/11/2020 | 25/05/2021 | M/S. D.K.H.CONSTRUCTION | 67.23 | 128.64 | 191.34 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | SM/06905 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mohanpur W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000745/2020-2021 |  | 15/12/2020 | 15/12/2020 | M/S. D.K.H.CONSTRUCTION | 30 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | SM/06905 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mohanpur W/S Scheme. |  |  | VCH/000857/2020-2021 |  | 05/02/2021 | 05/02/2021 | PULLOCK KUMAR GHOSH | 5 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | SM/06905 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001407/2020-2021 | 8443459 | 26/03/2021 | 26/03/2021 | MANABENDRA DAS | 0.16 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | SM/06905 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001408/2020-2021 | 8443459 | 26/03/2021 | 26/03/2021 | SUBRATA CHAKRABORTY | 0.17 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | SM/06905 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001409/2020-2021 | 8443459 | 26/03/2021 | 26/03/2021 | RINTU SAMANTA | 0.17 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | SM/06905 | Retrofitting | FHTC data entry. |  |  | VCH/001284/2021-2022 | 844363 | 18/01/2022 | 18/01/2022 | SANDIP MANNA | 0.12 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | SM/06905 | Retrofitting | FHTC data entry. |  |  | VCH/001285/2021-2022 | 844363 | 18/01/2022 | 18/01/2022 | TANMOY BERA | 0.21 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mohanpur Piped Water Supply Scheme. | SM/06905 | Retrofitting | Laying of Rising Main including interconnection for Augmentation of Mohanpur and its adjoining mouzas Water Supply Scheme within Mohanpur Block under Kharagpur Sub Division of Midnapore Division, P.H.E. Dte. |  |  | ORD/000640/2023-2024 | 5568/MD | 26/12/2023 | 25/01/2024 | GOBINDA MAITY | 6.55 | 0 | 0 | 0
Total | [13 empty] | 109.61 | 128.64 | 117.36