## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-II) PWSS | SM/06906 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Barisha (Zone-II) W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000216/2020-2021 | 1434/MD | 26/11/2020 | 25/05/2021 | UTTAM KUMAR DAS | 97.01 | 44.07 | 45.43 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-II) PWSS | SM/06906 | Retrofitting | Construction of SSP & Soak Pit at different places laying of pipe line of Barisha Zone -II . |  |  | VCH/000276/2022-2023 | BP-2022-23-34 | 29/04/2022 | 29/04/2022 | BIDHAN CHANDRA PATRA | 2.82 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Barisha (Zone-II) PWSS | SM/06906 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000105/2024-2025 | 3408/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.42 | 0 | 0 | 0
Total | [13 empty] | 112.25 | 44.07 | 39.26