## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000271/2020-2021 | 1468/MD | 26/11/2020 | 25/05/2021 | MASUM ALI KHAN | 86.17 | 96.39 | 111.86 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000729/2020-2021 |  | 15/12/2020 | 15/12/2020 | MASUM ALI KHAN | 20 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | REPAIRING OF WATER SWIVEL AND OTHER WORKS FOR RIG NO. SUPER RR UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000243/2021-2022 | 564/CMSD-II (D) | 26/11/2021 | 26/12/2021 | PADMA ENGINEERING & CO. | 4.08 | 3.98 | 97.43 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001414/2020-2021 | 8443461 | 26/03/2021 | 26/03/2021 | ARUP KR ADAK | 0.07 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001415/2020-2021 | 8443461 | 26/03/2021 | 26/03/2021 | PRATHA PRATIM PAL | 0.2 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001416/2020-2021 | 8443461 | 26/03/2021 | 26/03/2021 | ANIRBAN CHAKRABORTY | 0.17 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER MATERIALS & ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL AT (ZONE-II) TW-II (REPLACEMENT) OF BHEMWA W/S SCHEME IN SABANG BLOCK UNDER CDD, PHE DTE. |  |  | ORD/000055/2022-2023 | 244/CMSD-I (D) | 20/06/2022 | 05/07/2022 | MENAKA ENTERPRISE | 1.98 | 1.35 | 68.54 | 0
8 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT (ZONE-II) TW-II (REPLACEMENT) OF BHEMWA W/S SCHEME IN SABANG BLOCK UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000057/2022-2023 | 241/CMSD-I (D) | 20/06/2022 | 05/07/2022 | MENAKA ENTERPRISE | 2.64 | 2.53 | 95.79 | 0
9 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | PROVIDING HOUSING PIPE CONFORMING TO IS 12818:2010 WITH OTHER MATERIALS & ALLIED WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT (ZONE-II) TW-II (REPLACEMENT) OF BHEMWA W/S SCHEME IN SABANG BLOCK UNDER CDD, PHE DTE. |  |  | ORD/000058/2022-2023 | 242/CMSD-I (D) | 20/06/2022 | 05/07/2022 | MENAKA ENTERPRISE | 3.76 | 3.76 | 100 | 0
10 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & ALLIED WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT (ZONE-II) TW-II (REPLACEMENT) OF BHEMWA W/S SCHEME IN SABANG BLOCK UNDER CDD, PHE DTE. |  |  | ORD/000056/2022-2023 | 243/CMSD-I (D) | 20/06/2022 | 05/07/2022 | MENAKA ENTERPRISE | 1.98 | 1.86 | 93.5 | 0
11 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | REPAIRING OF DAMAGE TRUCK DRIVER CABIN, STEEL BODY, CHEQUER PLATE, CHASSIS AND TRUCK BODY PAINTING OF GOVT VEHICLE NO. WMK 6422 (TATA) UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000276/2022-2023 | 77/CMSD-I | 01/04/2022 | 16/04/2022 | M/S B.P.TRADING CORPORATION | 2.36 | 1.52 | 64.47 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | FHTC imis data entry. |  |  | VCH/001627/2021-2022 | 8443148 | 24/03/2022 | 24/03/2022 | NABOGOPAL ADHIKARI | 0.08 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | FHTC imis data entry. |  |  | VCH/001626/2021-2022 | 8443148 | 24/03/2022 | 24/03/2022 | MANABENDRA DAS | 0.15 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-I) PWSS | SM/06907 | Retrofitting | FHTC imis data entry. |  |  | VCH/001629/2021-2022 | 8443148 | 24/03/2022 | 24/03/2022 | SANDIP MANNA | 0.09 | 0 | 0 | 0
Total | [13 empty] | 123.74 | 111.39 | 90.02