## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Beluria Piped Water Supply Scheme. | SM/06908 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Beluria W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000720/2020-2021 |  | 15/12/2020 | 15/12/2020 | M/S. A.R. ENTERPRISE. | 35 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Beluria Piped Water Supply Scheme. | SM/06908 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Beluria W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000278/2020-2021 | 1470/MD | 26/11/2020 | 25/05/2021 | M/S. A.R. ENTERPRISE. | 92.63 | 69.1 | 74.59 | 100
Total | [13 empty] | 127.63 | 69.1 | 54.14