## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS | SM/06909 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000730/2020-2021 |  | 15/12/2020 | 15/12/2020 | HARIPADA PATTANAYAK | 30 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS | SM/06909 | Retrofitting | FHTC imis data entry. |  |  | VCH/001623/2021-2022 | 8443150 | 24/03/2022 | 24/03/2022 | PARTHA PRATIM PAL | 0.09 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS | SM/06909 | Retrofitting | FHTC imis data entry. |  |  | VCH/001624/2021-2022 | 8443150 | 24/03/2022 | 24/03/2022 | RINTU SAMANTA | 0.05 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS | SM/06909 | Retrofitting | FHTC imis data entry. |  |  | VCH/001625/2021-2022 | 8443150 | 24/03/2022 | 24/03/2022 | TANMOY BERA | 0.14 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS | SM/06909 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000272/2020-2021 | 1469/MD | 26/11/2020 | 25/05/2021 | HARIPADA PATTANAYAK | 83.93 | 33.53 | 39.96 | 100
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Retrofitting to accomodate FHTC under JJM in Bhemwa (Zone-II) PWSS | SM/06909 | Retrofitting | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Zone-II Pump House-II under Bhemwa water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001477/2022-2023 | 215/W/MMD | 10/02/2023 | 09/08/2023 | DEBJYOTI BASU | 11.23 | 0 | 0 | 100
Total | [13 empty] | 125.45 | 33.53 | 26.73