## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. | SM/06913 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chaupanya W/S Scheme, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000276/2020-2021 | 1451/MD | 26/11/2020 | 22/05/2026 | M/S. A.R. ENTERPRISE. | 94.15 | 57.2 | 60.75 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. | SM/06913 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chaupanya W/S Scheme, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000721/2020-2021 |  | 15/12/2020 | 15/12/2020 | M/S. A.R. ENTERPRISE. | 25 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. | SM/06913 | Retrofitting | Restoration of pipe line From Ramnagar to Mominpur SSK for Covering FHTC Work & Development of Land at H.W Site of Chaupanya PWSS within Kharagpur-II Block under Kharagpur Sub Division within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000504/2021-2022 | 2246/MD | 28/12/2021 | 18/01/2022 | MAMPI ENTERPRISE | 9.04 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. | SM/06913 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000103/2024-2025 | 3410/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.21 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chaupanya Piped Water Supply Scheme. | SM/06913 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chaupanya w/s Scheme. |  |  | BILL/00702/2024-2025 | 84434 | 03/05/2024 | 03/05/2024 | M/S. A.R. ENTERPRISE | 33.39 | 0 | 0 | 0
Total | [13 empty] | 173.79 | 57.2 | 32.91