## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | For FHTC Data Entry. |  |  | VCH/000852/2021-2022 | 844386 | 13/09/2021 | 13/09/2021 | SUBRATA CHAKRABORTY | 0.02 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | For FHTC Data Entry. |  |  | VCH/000851/2021-2022 | 844386 | 13/09/2021 | 13/09/2021 | SIDDHESWAR BAG | 0.1 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | FHTC Data entry |  |  | VCH/000632/2021-2022 | 8443121 | 23/08/2021 | 23/08/2021 | PARTHA PRATIM PAL | 0.01 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | Data Entry of FHTC. |  |  | VCH/000850/2021-2022 | 844386 | 13/09/2021 | 13/09/2021 | PAPPU SHAW | 0.05 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | FHTC Data entry |  |  | VCH/000634/2021-2022 | 8443121 | 23/08/2021 | 23/08/2021 | SHRABONTI BERA | 0.1 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-III) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000236/2020-2021 | 1440/MD | 26/11/2020 | 25/05/2021 | M/S. EL-CON | 70.72 | 27.4 | 38.75 | 100
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | Continuation work order ¿ Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre ,Health Care Institution etc¿. under Midnapore Division PHE Dte.for the period of 06 (months), from (01.01.2023 to 30.06.2023) |  |  | ORD/000635/2022-2023 | 764/MSSD | 31/12/2022 | 30/06/2023 | PULLOCK KUMAR GHOSH | 2.04 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | Functional Household Tap Connection data uploading charges in JJM_IMIS portal in Paschim Medinipur & Jhargram District under Jal Jeevan Mission |  |  | BILL/00732/2023-2024 | 844336 | 12/09/2023 | 12/09/2023 | PULLOCK KUMAR GHOSH | 2.04 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | Hire charges of Car No WB 33 D 6299 including supply of fuel and lubricants for the office of the Dy. SE, WC, PHE Dte. for the month of August. (MB No 3634/MD) |  |  | BILL/02032/2023-2024 | 84439 | 02/02/2024 | 02/02/2024 | PULLOCK KUMAR GHOSH | 1.69 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre, Health Care Institution etc. under Midnapore Division PHE Dte. Period from (15.07.2023 to 14.07.2024) |  |  | BILL/02177/2023-2024 | 844369 | 22/02/2024 | 22/02/2024 | PULLOCK KUMAR GHOSH | 2.33 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-III) PWSS | SM/06918 | Retrofitting | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre, Health Care Institution etc. under Midnapore Division PHE Dte. Period from (15.07.2023 to 14.07.2024) |  |  | BILL/02048/2023-2024 |  | 20/02/2024 | 20/02/2024 | PULLOCK KUMAR GHOSH | 2.33 | 0 | 0 | 0
Total | [13 empty] | 81.44 | 27.4 | 33.65