## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-IV) PWSS | SM/06921 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-IV) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000237/2020-2021 | 1441/MD | 26/11/2020 | 25/05/2021 | M/S. CARE | 52.92 | 3.4 | 6.42 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dherua (Zone-IV) PWSS | SM/06921 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-IV) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000716/2020-2021 |  | 15/12/2020 | 15/12/2020 | M/S. CARE | 7.86 | 0 | 0 | 0
Total | [13 empty] | 60.78 | 3.4 | 5.59