## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Chandkuri (Zone-II) PWSS | SM/06922 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandkuri (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000267/2020-2021 | 1464/MD | 26/11/2020 | 25/05/2021 | DULAL CHANDRA DAS | 80.8 | 113.52 | 140.49 | 0
Total | [13 empty] | 80.8 | 113.52 | 140.49