## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. | SM/06925 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasbazar W/S Scheme, Block: - Debra, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000263/2020-2021 | 1460/MD | 26/11/2020 | 25/05/2021 | SUBRATA DAS | 92.69 | 83.06 | 89.61 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. | SM/06925 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001149/2020-2021 | 8443110 | 12/02/2021 |  | PAPPU SHAW | 0.19 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. | SM/06925 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001150/2020-2021 | 8443110 | 12/02/2021 |  | SIDDHESWAR BAG | 0.21 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbazar Piped Water Supply Scheme. | SM/06925 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001151/2020-2021 | 8443110 | 12/02/2021 |  | SUBRATA CHAKRABORTY | 0.18 | 0 | 0 | 0
Total | [13 empty] | 93.27 | 83.06 | 89.05