## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Ragpur PWSS | SM/06927 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000102/2024-2025 | 3411/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.39 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Ragpur PWSS | SM/06927 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Ragpur W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000253/2020-2021 | 1449/MD | 26/11/2020 | 31/12/2024 | GOBINDA MAITY | 94.99 | 27.37 | 28.81 | 100
Total | [13 empty] | 107.39 | 27.37 | 25.49