## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kolanda Piped Water Supply Scheme. | SM/06928 | Retrofitting | Construction of Boundary wall & Land Development for Head work site of Kolanda & its adjoining mouzas Water Supply Scheme at Sabang Block under Midnapore Sadar Sub- Division within Midnapore Division, PHE. Dte. (81/EE/MD/2017-2018) |  |  | BILL/00420/2023-2024 | 844338 | 10/05/2023 | 10/05/2023 | KAILASH KUMAR AGARWALA | 1.44 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kolanda Piped Water Supply Scheme. | SM/06928 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kolanda W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000277/2020-2021 | 1452/MD | 26/11/2020 | 25/05/2021 | M/S. A.R. ENTERPRISE. | 86.63 | 101.07 | 116.66 | 77
Total | [13 empty] | 88.07 | 101.07 | 114.76