## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Rajnagar (Paschim) W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000245/2020-2021 | 1444/MD | 26/11/2020 | 25/05/2021 | BANERJEE CONSTRUCTION | 96.09 | 38.7 | 40.28 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Rajnagar W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000747/2020-2021 | null | 15/12/2020 |  | BANERJEE CONSTRUCTION | 30 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. |  |  | VCH/000279/2021-2022 | 8443118 | 31/05/2021 |  | TANMOY BERA | 0.11 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. |  |  | VCH/000280/2021-2022 | 8443118 | 28/05/2021 |  | SHRABONTI BERA | 0.17 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. |  |  | VCH/000281/2021-2022 | 8443118 | 31/05/2021 |  | SOVANDEB MANNA | 0.05 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. |  |  | VCH/000278/2021-2022 | 8443118 | 31/05/2021 |  | ANIRBAN CHAKRABORTY | 0.05 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. |  |  | VCH/000282/2021-2022 | 8443118 | 31/05/2021 |  | ARUP KR ADAK | 0 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000768/2021-2022 | 8443210 | 27/09/2021 |  | PARTHA PRATIM PAL | 0.11 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000767/2021-2022 | 8443210 | 27/09/2021 |  | NABOGOPAL ADHIKARI | 0.1 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Rajnagar (Paschim) PWSS | SM/06931 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000769/2021-2022 | 8443210 | 27/09/2021 |  | SANDIP MANNA | 0.1 | 0 | 0 | 0
Total | [13 empty] | 126.78 | 38.7 | 30.53