## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. | SM/06933 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sartla W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000728/2020-2021 |  | 15/12/2020 | 15/12/2020 | GOBINDA MAITY | 20 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. | SM/06933 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001146/2020-2021 | 8443107 | 12/02/2021 | 12/02/2021 | GANESH CH NANDY | 0.2 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. | SM/06933 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001145/2020-2021 | 8443017 | 12/02/2021 | 12/02/2021 | TANMOY BERA | 0.2 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. | SM/06933 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001147/2020-2021 | 8443107 | 12/02/2021 | 12/02/2021 | PARTHA PRATIM PAL | 0.03 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. | SM/06933 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001148/2020-2021 | 8443107 | 12/02/2021 | 12/02/2021 | SHRABONTI BERA | 0.2 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sartla Piped Water Supply Scheme. | SM/06933 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sartla W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000258/2020-2021 | 1455/MD | 26/11/2020 | 25/05/2021 | GOBINDA MAITY | 90.73 | 143.18 | 157.81 | 90
Total | [13 empty] | 111.38 | 143.18 | 128.56